## Slide 1: 475.04.03.02.01 TS Cold Mass Prototype
Giorgio Ambrosio
L3 deputy for the Transport Solenoid
Oct 21-24, 2014

## Slide 2: TS Cold mass assembly
Prototype

## Slide 3: TS Prototype = Coil#14#15 Module + Flanges
ground insulation
coil
pure Al sheet
for coil cooling
wedge
The coils are epoxy impregnated with the ground insulation and the Al sheet.
cooling tube
coil leads

## Slide 4: Goals
Allows validation of:
Design concept
Drawings
  Tolerances, fabrication and integration details
Coils and Shell Fabrication
  Achievable tolerances, procedure for He pipe, QC plan
Integration
  Procedure, gap  prestress
Performance

## Slide 5: Plan
The TS prototype is fabricated by FNAL-INFN collaboration
  INFN-Genoa group lead by P. Fabbricatore
FNAL is in charge of:
Prototype conductor procurement and QC
Complete CAD model
Coils drawings (envelope)
Shell fabrication drawings
Shell fabrication and QC
Shell instrumentation and Test
INFN is in charge of:
Coil fabrication and integration (vendor selected by INFN)
Supervision of work performed by vendor
FNAL & INFN: FEM modeling and interference decision

## Slide 6: FEM Analysis
3D model with average coil properties and actual dimensions (Wands)
2D model with measured coil properties and simulation of all assembly steps (Farinon)
Optimal rad. interference 3D: 100+ um
Optimal rad. interference 2D: 100-300 um
 Nominal rad. interference: 200 +/- 100 um

## Slide 7: Coil Fabrication
Coil #14
17 layers
Coil #15
18 layers

## Slide 8: Coil Electrical QC
Electrical tests:
  During winding:
    V_tot and layer-layer DV with 1 A
    Coil to ground at 1kV
  After impregnation:
    Inductance and resistance
    Coil to ground at 2 kV
    Coil to heaters at 1 kV
  After coil machining:
    Inductance and resistance
    Coil to ground at 2 kV
    Coil to heaters at 1 kV
    Impulse test at 1 kV
Both coils passed all tests

## Slide 9: Coil Dimensional QC
Dimensional tests:
  During winding:
    Min & Max radius at selected layers and positions
  After impregnation:
    ID, OD, height, coil sides parallelism
  After final machining:
    Inner radius (best fit, max inscribed, min circumscribed) and range
    Outer radius (best fit, max inscribed, min circumscribed) and range
    Sides: planarity and parallelism
    Concentricity, Perpendicularity,
    Roughness of outer surface.
Radius (mm) | Nominal | Tol. | Meas. | D_max* | RMS | Temp.
Coil #14 | 475.0 | +/-0.1 | 475.00 | -0.10/+0.08 | 0.05 | 21.8 °C
Coil #15 | 479.0 | +/-0.1 | 479.05 | -0.11/+0.08 | 0.05 | 22.3 °C
*With respect to measured Outer Radius

## Slide 10: Shell Fabrication
1. Forged cylinder
2. Rough machining of ID
3. Weld cooling pipes
4. Fine machining of ID based on coil
measurements at controlled temp.

## Slide 11: Shell QC
Cooling pipes ASME test:
  Hydrostatic Pressure Test at 83 Psig for 10 min
Dimensional tests:
  The shell looks very good
  All major dimensions are within tolerance
    Seen the impact on the flange flatness of welding the pipes
  Coil housing surfaces are acceptable
    Tolerance were very tight requiring temperature adjustment
Radius (mm) | Nominal | Tol.* | Meas. Max In | Meas. LS | Temp.
Coil #14 house | 474.78 | +/-0.025 | 474.78 | 474.83 | 20 °C
Coil #15 house | 478.83 | +/-0.025 | 478.81 | 478.86 | 20 °C
*+/-50 um on diameter

## Slide 12: Integration
Plan for shrink-fit integration:
  Warm up shell
  Insert coil A
  Lock coil A in place
  Insert coil B
  Lock coil B in place
  Let shell cold down
  Put stycast to fill gap between coil-side and wedge
  Install wedge and side flange
  Repeat steps 7 and 8 on the other side
Hard copy of integration tooling is available (proprietary)

## Slide 13: Integration
Prototype Integration
Oct 20-24

## Slide 14: Integration QC & Acceptance Tests - I
Electrical:
  Coil to Ground
  Heater to Coil
  Inductance & Resistance of each coil
  Impulse test
Prestress:
  Strain gauge readings (after vs. before integration)
  Shell OD CMM measurements (after vs. before integration)

## Slide 15: Integration QC & Acceptance Tests - II
Dimensional tests:
  CMM to evaluate impact of integration on all interfaces
Cooling pipes and joints:
  ASME pressure test
Warm Magnetic Measurements:
  Stretched wire measurements
    Each coil separately

## Slide 16: Cold Tests
Cold electrical check out
  Hi-pot tests (coil-ground; heaters-coil)
Cooling tests:
  Temperature profile vs. cooling rate
Cold powering:
  Up to nominal current
  Up to 120% nominal current (same Ic margin as in operation)
  Reverse polarity: up to 60% nominal current (Max axial force vs. flange)
Warm up: measure RRR

## Slide 17: Goals Summary
Allows validation of The prototype has validated:
Design concept
Drawings
  Tolerances, fabrication and integration details
Coils and Shell Fabrication
  Achievable tolerances, procedure for He pipe, QC plan
Integration
  Procedure, gap  prestress
Performance
To be demonstrated in Feb./Mar. 2015
Drawings for tender in progress
Contract to be placed after Prototype test

## Slide 18: Back-up Slides

## Slide 19: Design - Conductor
Conductor Parameter | Unit | Design Value |  | Measured Value
Cable critical current at 5T, 4.2K | A |  | 5900 | 5950-6300
Number of strands |  |  | 14 | 
Strand diameter | mm |  | 0.67 | within tolerances
Strand copper/SC ratio |  |  | 1 ± 0.05 | 0.97-1.02
Initial RRR of Cu matrix |  |  | 150 | 100-104
Filament size | µm |  | < 30 | 25.5-25.7
Strand twist pitch | mm |  | 15 ± 2 | 15.8-15.9
Rutherford cable width | mm |  | 4.79 ± 0.01 | within tolerances
Rutherford cable thickness | mm |  | 1.15 ± 0.006 | within tolerances
Al-stabilized cable width (bare) at room temperature | mm |  | 9.85 ± 0.05 | within tolerances
Al-stabilized cable thickness (bare) at room temperature | mm |  | 3.11 ± 0.03 | within tolerances
Initial RRR of Aluminum stabilizer |  |  | > 800 | 925-1160
Aluminum 0.2% yield strength at 300 K | MPa |  | > 30 | 45-56
Aluminum 0.2% yield strength at 4.2 K | MPa |  | > 40 | 74-84
Shear strength between Aluminum and NbTi strands | MPa |  | > 20 | 35-46
Iop = 1730 A
Jeng ~ 50 A/mm2
Iop/Ic~= 58% (at 5.1 K, 3.4 T)
Temp margin = 1.5 K