## Slide 1: Mu2e Accelerator Systems Overview: Muon Campus Projects, Procedures
Steve Werkema
Mu2e Accelerator Level 2 Manager
10/21/2014

## Slide 2: Outline
Muon Campus Projects
Key Performance Parameters
Cost Estimating Procedures
Risk Management
Interface Management
Miscellaneous
Breakout talks

## Slide 3
Muon Campus Projects

## Slide 4: The Fermilab Muon Campus
Three General Components:
AIPs and GPPs (AIP = Accelerator Improvement Project, GPP = General Plant Project)
Mu2e project
g-2 project
g-2
Mu2e
Former Anti-proton Source

## Slide 5: Scope of Muon Campus Projects
Recycler RF AIP
Recycler 2.5 MHz RF
Delivery Ring 2.4 MHz RF cavity and High Level system
g-2
Delivery Ring AIP
Mu2e
Beam Transport AIP
Single bunch extraction from Recycler
Beamline Aperture upgrades
Beam transport to Delivery Ring
M5
g-2 is responsible for the D30 Straight Section reconfiguration and extraction from the Delivery Ring (different devices used for g-2 and Mu2e)
The Delivery Ring AIP is responsible for Delivery Ring injection devices (common)
D10
D50
D30
(AIP = Accelerator Improvement Project)
MC Beamline Enclosure GPP
M4

## Slide 6: Mu2e Scope Overview
Mu2e
Bldg
MC-1
Bldg
475.02.03 Instrumentation & Controls
475.02.04 Radiation Safety
475.02.05 Resonant Extraction
Delivery Ring
475.02.06 Delivery Ring RF
475.02.07 External (M4) Beamline
475.02.08.02 Extinction
475.02.08.03 Extinction Monitor
475.02.09 Target Station
Everywhere
×
Notes: Note: Kautz Road will not be routed around the Mu2e building – hence the big red X.

## Slide 7: Required New Construction Not on the Mu2e Project
Accelerator Upgrade | Project
MI-8 beamline to Recycler Ring Injection | NOvA Project
Recycler Ring 2.5 MHz RF system | Recycler RF AIP
Delivery Ring 2.4 MHz RF Cavities and HL Amps & Cooling | Recycler RF AIP
Single bunch extraction from Recycler Ring | Beam Transport AIP
Beamline aperture upgrades | Beam Transport AIP
AP1, AP2, AP3 to M1, M2, M3 conversion & upgrade | Beam Transport AIP
Beam transport instrumentation & infrastructure | Beam Transport AIP
Beam transport controls | Delivery Ring AIP
Delivery Ring Injection | Delivery Ring AIP
Delivery Ring Abort | Delivery Ring AIP
Delivery Ring infrastructure | Delivery Ring AIP
Delivery Ring Controls and Instrumentation | Delivery Ring AIP
D30 straight section reconfiguration | g-2 Project
Delivery Ring Extraction (except ESS) | g-2 Project
Extraction line (M4) to M5 split | g-2 Project
M4 beamline enclosure | MC Beamline Enclosure GPP

## Slide 8: Why Would We Do This to Ourselves?
Advantages
Exploits the common requirements of Mu2e and g-2. Integrated planning to meet these requirements reduces the combined cost of these two projects
Scheduling: moving scope that must be accomplished early to AIPs allows implementation to begin before CD-3 for either project –
  Muon Campus construction is underway now and neither Mu2e or g-2 have CD-3.
  Without this scheduling flexibility the g-2 run would start later (1 – 2 years) which would delay the start of the Mu2e run
Why many AIPs?
  Collect common scope
  Keep AIP TPCs below $10M maximum
Risk
Complicated interdependence … a setback in one project may affect the others
Mitigation: This risk is mitigated by continuous management attention
  Monthly PMGs (Mu2e, g-2, Muon Campus) and POGs
  Key management straddles Muon Campus project boundaries (next slide)
  Interface Milestones maintained by the Muon Campus Program Coordinator

## Slide 9: Muon Campus Program Organization
MC-1 Building GPP
Project Director
E. Gottschalk (PPD)
Project Manager
R. Alber (FESS)
MC Infrastructure Upgrade GPP
Project Director
R. Ortgiesen (FESS)
Project Manager
T. Lackowski (FESS)
MC Delivery Ring AIP
Project Director
G. Annala (AD)
Project Manager
G. Annala (AD)
L2 Beamlines: J. Morgan
L2 Ctrls Instrum: B. Drendel
MC Beamline Enclosure GPP
Project Director
G. Annala (AD)
Project Manager
T. Lackowski (FESS)
MC Cryo Plant AIP
Project Director
G. Annala (AD)
Project Manager
A. Klebaner (AD)
MC Recycler RF AIP
Project Director
I. Kourbanis (AD)
Project Manager
I. Kourbanis (AD)
Chief Accelerator Officer
S. Nagaitsev
MC Beam Transport AIP
Project Director
G. Annala (AD)
Project Manager
I. Kourbanis (AD)
L2 Beamlines: J. Morgan
L2 Ctrls Instrum: B. Drendel
Muon Campus Program Coordinator
M. Convery (AD)
Accelerator Division Head
S. Nagaitsev
Deputy Chief Research Officer
G. Bock
Particle Physics Division Head
P. McBride
Mu2e
R. Ray (PPD)
L2 Accelerators
S. Werkema (AD)
L3 Ext Beamline: D. Still
L3 Ctrls Instrum: B. Drendel
Install Coord: C. Gattuso
Beamline Mech E: C. Ader
g-2
C. Polly (PPD)
L2 Accelerators
M. Convery (AD)
L3 Beamlines: J. Morgan
L3 Ctrls Instrum: B. Drendel
Install Coord: C. Gattuso
Beamline Mech E: C. Ader
AIP Installation Coordinator
C. Gattuso (AD)
AIP Beamline Mechanical Engineer
C. Ader (AD)
Same team working on Mu2e accelerators, g-2 Accelerators, and AIP beamlines (Muon Dept.)
Common installation coordinator and beamline mechanical engineer

## Slide 10: Interface Milestones
Interface milestone document under configuration control in the Beams Document Database
Maintained by the Muon Campus Program Coordinator (Mary Convery)

## Slide 11
Mu2e Accelerator Systems Key Performance Parameters

## Slide 12: Mu2e Accelerator KPPs
Threshold Performance
  All accelerator components, RF and resonant extraction components are installed and tested at nominal voltages and currents.
  All target station components are complete, delivered to Fermilab and tested. Heat and Radiation Shield is installed in Production Solenoid. Other components are ready to be installed after field mapping.
  Shielding designed for 1.5 kW operation delivered.
Objective Performance
Protons are delivered to the diagnostic absorber in the M4 beamline.
Shielding designed for 8 kW operation delivered.
Note: the commissioning of beam from the Delivery Ring to the Diagnostic Absorber is off-project

## Slide 13
Cost Estimating Procedures
Mu2e BOEs
BOE Review

## Slide 14: Cost Estimate Procedure
Project Controls (Mike Gardner) generates a BOE Report that contains an entry for every activity in the schedule (example on next slide).
  Sent to every L3 manager and selected L4 managers. Posted to Mu2e-doc-3001
  Updated at least Monthly
L3 and L4 managers in consultation with technical experts enter the resources, estimate uncertainties, and estimate types into the BOE report and return it to project controls.
Project Controls meets face-to-face with each L3/L4 manager to transfer the resource data into the schedule along with any associated schedule logic. This is an iterative process – adjustments are made as the schedule and cost estimates evolve.
L3 and L4 managers generate BOE Forms (details later) that contain the justification for the resources loaded for each activity.
Review: BOEs are reviewed at all levels: preparers, CAMs, L2 management

## Slide 15: BOE Report
WBS | WBS Name | Activity ID | Activity Name | Most Likely Duration | Estimate Type Activity Level | Division / Section | Resource Name | Most Likely Units | Estimate Uncertainty Factor | Resource Note | Predecessors | BOE DocDB
475.02W.03.01.1 | Transport Controls and Delivery Ring Controls | 47502.03.01.1.001195 | Coordinate Implementation Plan with Delivery Ring AIP | 30 | L3 | AD | Control System Engineer | 8 | 0.25 | G Brown | 47502.03.01.1.001190 | 3703
 |  | 47502.03.01.1.001200 | Purchase Network & Communication Hardware Implementation and Closeout | 30 | M4 |  | M&S Standard with Base Year FY14 | 5000 | 0.25 | Repurposed / Pro Card | 47502.01.02.001050, 47502.03.01.1.001195 | 3703
 |  | 47502.03.01.1.001220 | Abort Link Implementation | 60 | L4 | AD | Engineering Physicist | 10 | 0.3 | A Franck | 47502.03.01.1.001200 | 3703
 |  |  |  |  |  |  | Electronics Design Engineer | 100 | 0.3 | D McArthur | 47502.03.01.1.001200 | 3703
 |  |  |  |  |  |  | Control System Engineer | 47 | 0.3 | G Vogel | 47502.03.01.1.001200 | 3703
 |  | 47502.03.01.1.001230 | Camac and Timing Links Implementation and Closeout | 60 | L4 | AD | Electronics Technician | 40 | 0.3 | TBD | 47502.01.02.001050, 47502.03.01.1.001200 | 3703
 |  |  |  |  |  |  | Control System Engineer | 10 | 0.3 | G Vogel | 47502.01.02.001050, 47502.03.01.1.001200 | 3703
 |  | 47502.03.01.1.001240 | Network Installation Implementation and Closeout | 60 | L4 | AD | Electronics Technician | 16 | 0.3 | S Conlon | 47502.03.01.1.001200 | 3703
 |  |  |  |  |  |  | Control System Engineer | 8 | 0.3 | G Brown | 47502.03.01.1.001200 | 3703
475.02W.03.01.2 | Mu2e Experimental Hall Controls | 47502.03.01.2.001090 | Purchase Controls Hardware | 30 | M3 |  | M&S Standard with Base Year FY14 | 31000 | 0.15 |  | 47502.01.02.001050, FY18B02 | 3553
 |  | 47502.03.01.2.001110 | Purchase Network and Communication Hardware | 30 | M3 |  | M&S Standard with Base Year FY14 | 45800 | 0.15 |  | 47502.01.02.001050, FY18B02 | 3553
 |  | 47502.03.01.2.001130 | Pull Innerduct | 4 | M4 |  | Electrician | 128 | 0.3 | Assumes 4 day pull for 4 workers | 47502.03.01.2.001110, 47502.03.01.2.001120 | 3553
 |  | 47502.03.01.2.001140 | Pull Cable CrossGallery(Xgal) to Mu2e | 5 | M4 |  | Electrician | 160 | 0.3 | 5 day pull for 4 workers | 47502.03.01.2.001130, 47502.03.01.2.001100, 47502.03.01.2.001090 | 3553
 |  | 47502.03.01.2.001150 | Pull Cable AP30 to Mu2e | 3 | M4 |  | Electrician | 96 | 0.3 | 3 day pull for 4 workers | 47502.03.01.2.001140, 47502.03.01.2.001100, 47502.03.01.2.001090 | 3553
 |  | 47502.03.01.2.001160 | Terminate Connectors | 20 | M4 |  | Electrician | 64 | 0.3 | Fiber Terminations | 47502.03.01.2.001150, 47502.03.01.2.001140, 47502.03.01.2.001130 | 3553
 |  | 47502.03.01.2.001170 | Controls Infrastructure | 60 | L3 | AD | Electrical Technician | 47 | 0.2 | M Colburn (FIRIS) | 47502.03.01.2.001160 | 3553
 |  |  |  |  |  |  |  | 94 | 0.2 | TBD | 47502.03.01.2.001160 | 3553
 |  |  |  |  |  |  | Control System Engineer | 14 | 0.2 | G Vogel | 47502.03.01.2.001160 | 3553
 |  |  |  |  |  |  |  |  |  | A Franck | 47502.03.01.2.001160 | 3553
 |  | 47502.03.01.2.001180 | Network Infrastructure | 60 | L3 | AD | Electrical Technician | 9 | 0.2 | S Conlon | 47502.03.01.2.001160 | 3553
 |  |  |  |  |  |  | Control System Engineer | 5 | 0.2 | G Brown | 47502.03.01.2.001160 | 3553
 |  | 47502.03.01.2.001190 | HRM Installation | 60 | L3 | AD | Electrical Technician | 188 | 0.2 | TBD | 47502.03.01.2.001160 | 3553
 |  |  |  |  |  |  | Control System Engineer | 4 | 0.2 | G Vogel | 47502.03.01.2.001160 | 3553
 |  |  |  |  |  |  | Computing Services Specialist | 64 | 0.2 | TBD | 47502.03.01.2.001160 | 3553
This is a small portion of the Instrumentation and Controls part of the BOE report
The BOE Report is a working document
The BOE Report is the vehicle by which the L3, L4 managers and project controls communicate with one another about schedule and resource information
Notes: all of the required information is entered in this example

## Slide 16: Access to Mu2e BOEs
Mu2e Accelerator BOEs are accessible from the Accelerator page on the review web site:
http://mu2e.fnal.gov/public/project/reviews/cd2-review/accel.shtml
The Mu2e doc # links take you to the Mu2e doc DB item containing the BOE and its supporting documents.

## Slide 17: BOE Doc DB contents
BOE Form
(Often there are more than one)
Supporting Documents
BOE Review and Response
BOE Report spreadsheet

## Slide 18: Mu2e BOE – Page 1
Supporting Documents – all available in the same doc DB item
BOE Review
BOE Baseline date = May 1, 2014
M&S in 2014 dollars
Notes: I will not show the BOE change log

## Slide 19: Mu2e BOE – Page 3ff
There is an entry for each Activity in the schedule
Contingency and contingency rule used are cited (Called “Estimate Uncertainty” in schedule)
Each Resource this activity is listed with quantities and justification
.
.
.

## Slide 20: BOE Review
This is an excerpt from a BOE review form (Mu2e-doc-4265) for the BOE shown in the preceding slides.
The BOE review checks the following:
that all the required information is present and correct
the information given actually supports the cost estimate given
contingency rules are properly applied
resources given match the Mu2e schedule in P6
that all costs have been accounted for

## Slide 21
Risk Management

## Slide 22: Risks
22 Accelerator Risks in Risk Register
  All risks mitigated to the extent possible
  8 Threats
    4 High
    3 Medium
    1 Low
  2 Opportunities
  12 Retired Risks
Detailed mitigation plans for all risks are documented in risk forms in the Mu2e doc DB and are linked from the Risk Register (docdb column)
All risks are understood and under control
Details on specific risks will be provided in the breakout session

## Slide 23: Risk Register
Links to risk forms
Notes: The link to the Mu2e Risk Register can be found on the Review Web site on the Documentation Home page.

## Slide 24
Interface Management

## Slide 25: Project Interface Matrix
Accelerator Interface Document
Available on Project Management page of the review web site under “Requirements and Interface Documents”
Notes: All interfaces with WBS 475.03 (Conventional Construction) are under change control and have been formally signed by the interface owners.

## Slide 26: Accelerator Interface Document
Accelerator Interface Document is divided into two sections:
  Internal interfaces – interfaces of each Accelerator L3 with other Accelerator L3s
  External Interfaces – interfaces of each Accelerator L3 with other Mu2e L2s and other Muon Campus projects
The Accelerator Interface document is available from the review web site

## Slide 27: Accelerator Interface Document (continued)
Extract from the Accelerator Interface Document for External Beamline external interfaces
Owners are the L3 manager for the External Beamline and one of the following:
  The L2 manager for the indicated Mu2e L2, or
  The AIP/GPP/g-2 manager indicated by name
Reference Documents/Drawing will be created and signed by the owners prior to CD-3c

## Slide 28
Miscellaneous
Technical Documentation

## Slide 29: Project Management Costs
Project management costs for L2 management is in the Accelerator Project management L3.
Project management activities and costs for each L3 are contained in a L4 category called “Technical Documentation”

## Slide 30
Mu2e Accelerator Breakout Session Talks

## Slide 31: Mu2e Accelerator Breakout talks
Title | File | Speaker | Time (min)
Mu2e Accelerator Overview | B02-1 Accelerator Overview | S. Werkema | 30
Radiation Safety | B02-2 Radiation Safety | A. Leveling | 30
Delivery Ring RF | B02-3 Delivery Ring RF | J. Dey | 20
Target Station | B02-4 Target Station | R. Coleman | 50
Resonant Extraction | B02-5 Resonant Extraction | V. Nagaslaev | 30
External Beamline Design | B02-6 External Beamline Design | E. Prebys | 20
External Beamline Cost & Schedule | B02-7 External Beamline Cost-Sched | D. Still | 20
Instrumentation & Controls | B02-8 Instrumentation-Controls | B. Drendel | 30
Extinction | B02-9 Extinction | E. Prebys | 30
Extinction Monitoring | B02-10 Extinction Monitoring | P. Kasper | 30
Installation & Commissioning | B02-11 Installation-Commissioning | S. Werkema | 20
>>> Not shown in chronological order

## Slide 32: Proposed Schedule
Tuesday Afternoon (3:10 – 5:00 pm) Combined Session
  Accelerator Overview S. Werkema 40 min
  Muon Beamline Overview G. Ginther 40 min
  Muon Beamline Vacuum D. Pushka 30 min
Wednesday Morning (8:00 – 11:30 am)
  Target Station R. Coleman 60 min
  Radiation Safety A. Leveling 40 min
  Break 10 min
  Delivery Ring RF J. Dey 30 min
  Resonant Extraction V. Nagaslaev 40 min
  Instrumentation & Controls B. Drendel 40 min
Notes: 10 min. added to talk durations to allow time for questions and discussion.

## Slide 33: Proposed Schedule (continued)
Wednesday Afternoon (12:30 – 2:00 pm)
  External Beamline Design E. Prebys 30 min
  External Beamline Cost & Schedule D. Still 30 min
Thursday Morning (8:00 – 11:30 am)
  Extinction E. Prebys 40 min
  Extinction Monitoring P. Kasper 40 min
  Installation and Commissioning S. Werkema 20 min
Notes: 10 min. added to talk durations to allow time for questions and discussion.