## Slide 1: Mu2e DOE Review Construction Coordination
Ron Foutch P.E.
Construction Coordinator / Civil Engineer
10/22/2014

## Slide 2: Construction Coordination
Construction Coordinator (FCC) - Tim Trout
  Tim’s resume:
    * B.A. in Geology
    30 + years experience overseeing and managing heavy industrial /
    commercial construction projects.
  The Fermilab FCC is the primary point of contact with the Subcontractor on a daily basis. He is the Fermi Competent Person a defined by OSHA.
  The Fermilab FCC is a Fermilab person specifically assigned to oversee the work of a project for conformance to the subcontract requirements.
  The Fermilab FCC is the only person allowed to authorize field directives to the subcontractor with the exception of the Fermilab Procurement Officer. Supplemental agreements are issued by the Fermi Procurement Officer to incorporate the field directive into the contract.
  -
Notes: Tim Trout has been assigned to be the Fermilab Construction Coordinator for the Mu2e project.
As outlined in the Exhibit A - His responsibilities as the C.C. is
  To be the primary point of contact with the Subcontractor on a day to day basis. In other words - He will act as the liaison between the Lab and the subcontractor. He will be the boots on the ground – The eyes and ears in the field for the Lab.
  Tim will oversee the project for conformance to the subcontractor requirements ( i.e. – Drawings & Specifications)
  He has the authority to field direct the subcontractor to a Level of $5K.
Tim comes with a huge amount of experience. He has a B.A. in Geology. And, over 30 years of experience overseeing and managing heavy industrial / commercial construction projects both in private and governmental sectors. More importantly, Tim just finished a project (MC-1) which is just adjacent to this project. This building footprint is almost the same. So, Tim is very familiar with the surroundings (Existing Utilities) and soil conditions for the excavation of this project. He is also very familiar and aquainted with local occupants / users in the area. All of this makes Tim is an excellent choice for the C.C on this project.

## Slide 3: Construction Coordination
Preconstruction Meeting:
  Checklist Items:
    Introduction of the Project Team
      Roles and Responsibilities of each Project Team member
    ES& H Items:
      Integrated Safety Management (ISM)
      Subcontractor ES&H Plan (Safety Plan)
      Soil Erosion and Control Plan (SWPPP)
      Project Hazard Analysis (H.A.)
      Fermilab Emergency Procedures
      Accident Reporting Requirements
      Employee Safety Training:
      Project Safety Inspections : DOE & Lab
      Construction Permits:
      Radiological or Controlled Areas
      Security Issues
Notes: Prior to the Fermilab Procurement Dept. issuing the Notice to Proceed (N.T.P) to the Subcontractor to begin the work a Preconstruction Meeting is held. This meeting is a very important. It highlights many key points of the contact documents. First and foremost, it establishes the Lab’s expectations relating to Environmental, Safety, Health and Quality (ESH&Q) requirements. Checklists are used to help guide the meeting discussion. The checklist as it relates to the Construction Management includes topics as listed here :
Introduction of the Project Team - Introduce each member of the Project Team (Lab’s and Subcontractor’s side) to one another. In many cases this is the first time some of the members will see each other face to face. So, this gives a face to the name.
Roles and Responsibilities of the Project Team – The roles and responsibilities are generally discussed for each member attending this meeting. (On the Lab side this would include the Construction Manager, Construction Coordinator, ES&H Representative and the Procurement Officer) One the subcontractor side this would include the Project Manager, Superintendent, Safety Representative / OSHA Competent Person)
ADDITIONAL NOTES TO BE ADDED

## Slide 4: Construction Coordination
    Quality Control Items:
      Project Quality Control Plan (PQC)
      Material Submittals Management
      Quality Control Services – Testing and Inspection
      Subcontractor Quality Control Manager implements PQC by implementing:
          Preparatory Phase
          Initial Phase
          Follow-up Phase
  Brief Review of Addendum A and Exhibit A
      Scope of Work
      Items Affecting the Work Planning
      Materials and Services Furnished by Fermilab
      Construction Schedule – Cost Loaded – Milestone Definitions
      Issuance of Notice to Proceed (N.T.P.)
Notes: NOTES TO BE ADDED

## Slide 5: Construction Coordination
Weekly Construction Meeting:
  Weekly Meeting Agenda
    Project Status
      Percentage of Completion
      Achievements of each Pacing Milestone
    Safety Issues
      Safety Performance
        OSHA Recordable accidents
        Total Worker Hours
      Environmental Concerns
        Erosion Control Report
      DOE / Lab ESH&Q Inspections
        Findings
        Recommendations
        Noteworthy Practices
      Quality Control Reports
Notes: A major tool in the Construction Management responsibilities to conduct a Weekly Construction Meeting.
ADDITIONAL NOTES TO BE ADDED

## Slide 6: Construction Coordination
Weekly Construction Meeting:
  Present Status
  Activity / Construction Planned
    Two week look ahead schedule reviewed
  Shutdown Interfaces and / or Work in Sensitive areas
    Utility outages
    Road closings, Working in occupied areas & etc.
  Problem Area / Changes / QA topics
  Request for Information (RFI) Issues
  Deficiency List
Notes: NOTES TO BE ADDED

## Slide 7: Construction Coordination
Status updates
  Construction Coordinator verifies subcontractor's stated progress on a monthly basis.
  Measuring against the subcontractors schedule of values, the earned value is assembled.
Construction Close Out:
  Beneficial Occupancy
  Punch List
  Final Acceptance
Notes: ADDITIONAL NOTES TO BE ADDED