## Slide 1: Mu2e Tracker Management
A. Mukherjee
Tracker L2 Manager
7/8/2014

## Slide 2: Cost Table
 | Base Cost (AY K$) |  |  | Estimate Uncertainty (on remaining costs) | % Contingency on ETC | Total Cost
 | M&S | Labor | Total |  |  | 
475.06 Tracker |  |  |  |  |  | 
475.06.01 Tracker Project Management |  |  |  |  |  | 
475.06.01.02 Preliminary & Final Design (Post CD-1; PED) | 6 | 532 | 539 | 6 | - | 545
475.06.01.03 Implementation & Close-out (Post CD-3; Line Item) | 21 | 1,247 | 1,268 | 243 | 19% | 1,512
Grand Total | 28 | 1,779 | 1,807 | 250 | 20% | 2,057

## Slide 3: Cost Breakdown
Base Cost (AY K$)
Chart: 
| 475.06.01.02 Preliminary & Final Design (Post CD-1; PED) | 475.06.01.03 Implementation & Close-out (Post CD-3; Line Item)
Total | 538612.6759 | 1268377.1073
Chart: 
| L Labor | M Material
Total | 1779429.6197 | 27560.1635

## Slide 4: Quality of Estimate
Base Cost (AY K$)
Chart: 
| L1 Actual / M1 Existing P.O. | L2 LOE Task / M2 Procurements for LOE/Oversight Work | L3 / M3 Advanced | L4 / M4 Preliminary | L5 / M5 Conceptual | L6 / M6 Pre-Conceptual | L7 / M7 Rough Estimate Pre-Conceptual - Uncommon Work
Total | 476007.3669 | 1306392.9966 | 0.01 | 24589.4497 | 0.01 | 0.01 | 0.01

## Slide 5: Labor & Material by FY
Base Cost (AY K$)
Chart: Annual Cost $K
| 42277 | 42643 | 43008 | 43373 | 43738 | 44104 | 44469
L Labor | 195862.7347 | 202149.0701 | 224803.2983 | 212964.4523 | 220872.3272 | 189256.8394 | 1319.703
M Material | 5495.7218 | 311.1306 | 9203.5212 | 2913.4337 | 709.8662 | 2291.3214 | 223.6874
Non-Fermi Labor
Cumulative Total | 739971.1324 | 942431.3331 | 1176438.1526 | 1392316.0386 | 1613898.232 | 1805446.3928 | 1806989.7832

## Slide 6: Labor Resources by FY
FTEs by Discipline
Chart: Annual FTE's
| 42277 | 42643 | 43008 | 43373 | 43738 | 44104 | 44469
AD Administrative | 0.3362 | 0.3376 | 0.3236 | 0.3011 | 0.3061 | 0.2444 | 0.0016
EN Engineering | 0.5683 | 0.5705 | 0.6339 | 0.566 | 0.5683 | 0.4709 | 0.0032
ES Environmental, Safety & Health
FM Facilities Management
IT Information Technology
SC Scientific | 0.334 | 0.1132 | 0.1123 | 0.1123 | 0.0557 | 0 | 0
TE Technical | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative | 3.7486 | 4.7699 | 5.8397 | 6.8191 | 7.7492 | 8.4645 | 8.4693