## Slide 1: Mu2e Tracker University Roles in Construction
Marj Corcoran
L3 manager for Straw Assemblies
October 22, 2014

## Slide 2: Institutions and faculty/scientists
York College at CUNY—Jim Popp and Kevin Lynch
University of Minnesota—Dan Cronin-Hennessy
Rice University—Marj Corcoran
University of Houston—Ed Hungerford and Kwong Lau
Duke University—Seog Oh and Chiho Wang
Fermilab—Aseet Mukherjee, Bob Wagner, Vadim Rusu

## Slide 3: York College at CUNY
York will
prepare all straw end pieces (50K with spares)
leak test in vacuum a few % of all straws as validation of the CO2 leak tests
develop QA/QC database with Minnesota
design and fabricate vacuum feedthroughs
Vacuum setup and lab space at York

## Slide 4: York vacuum setup
Straws are tested in vacuum with 1atm ArCO2 gas. A few percent of all straws will be tested in vacuum to validate the CO2 leak tests (discussed later).

## Slide 5: York – straw end piece assembly
York will also assemble the end straw pieces. The fixturing for this work has been developed at Fermilab.

## Slide 6: York QA database
York is developing the QA database, drawing on the expertise at Minnesota.

## Slide 7: University of Minnesota
Minnesota will
Leak test all straws (25K including spares)
Cut straws to length and insert straw terminations
Work with York on QA database
Some of the available lab space at Minnesota

## Slide 8: CO2 Straw Leak Tests
Since the straws operate in vacuum, it is important to ensure that all straws have
leak rates below our limit of 30 x 10-5 ccm. We will test 100% of the straws
using a technique we developed using CO2 sensors with Ar/CO2 gas in the straws.
This is the CO2 test chamber, currently at Lab 3 in the Village.

## Slide 9: CO2 straw leak tests
We flush the chamber with N2, pressurize the straw with Ar/CO2 to 1atm above ambient, insert it in the chamber, and wait about an hour. The sensor reads the CO2 levels in ppm, providing a 10-15% measurement of the leak rate.

## Slide 10: CO2 leak test—first 100 straws
We tested 119 straws over this past summer, here are the measured leak rates.

## Slide 11: Minnesota--Straw preparation
Minnesota will cut the straws to length and glue in the end pieces. Minnesota post doc Dan Ambrose already has experience with these tasks.

## Slide 12: Rice University
Rice will
Construct 96-straw panels (220 including spares)
Run some preliminary tests
Rice clean room

## Slide 13: Panel assembly
This is the Panel Assembly and Alignment Structure (PAAS). This is the configuration for stringing sense wires.

## Slide 14: Panel assembly
This is an example of the 3D printed piece that will be used to position the straws. The dowel pins in the previous picture are replaced with these pieces.

## Slide 15: University of Houston
University of Houston will
Test all panels including HV tests, continuity, signal readout
Check all tensions in both straws and wires
UH is prepared to help with leak tests if needed
Constructing the MEGA drift chamber and some of the UH lab space.

## Slide 16: Duke University
Duke will
Procure the straws from PPG and perform several tests
Use X-ray machine from the Atlas TRT construction to locate each wire
X-ray setup at Duke

## Slide 17: Duke X-ray wire location
Taken from a talk by Chiho Wang last year

## Slide 18: Fermilab
Fermilab will
Leak test each panel in vacuum
Assemble panels into planes and construct the full tracker
Vacuum tank in Lab 3 at Fermilab

## Slide 19: ES&H considerations
Each university has its own ES&H department, and each group will have to abide
by the regulations of its university.
That said, each institution should
Have a written safety document for the work done there
Have a one-on-one safety discussion with each person working there
Have periodic safety inspections.
There are not a lot of hazards:
Compressed gas
Soldering irons and solder
Epoxy and other chemicals
X-rays

## Slide 20: Parts flow
Duke
Rice U. Houston
York
PPG
U. Minnesota
Straws
Termination
Vacuum Feedthroughs
Panels
Vender Oversight
York assembles end pieces, ships to MN
MN leak tests straws, inserts end pieces, ships to Rice
Rice assembles panels, takes to UH
UH runs extensive test on all panels, ships to Duke
Duke measures wire positions, ships to Fermilab

## Slide 21: Cost Table
 | Base Cost (AY K$) |  |  | Estimate Uncertainty (on remaining costs) | % Contingency on ETC | Total Cost
 | M&S | Labor | Total |  |  | 
475.06 Tracker |  |  |  |  |  | 
475.06.03 Straw Assemblies |  |  |  |  |  | 
475.06.03.01 Panels | 648 | 269 | 917 | 443 | 57% | 1,361
475.06.03.02 Single Plane | 145 | 98 | 243 | 67 | 39% | 310
475.06.03.03 Gas Manifold | 1,722 | 151 | 1,873 | 749 | 42% | 2,623
475.06.03.04 Full Tracker Support and Assembly | 193 | 292 | 485 | 234 | 51% | 718
Grand Total | 2,708 | 811 | 3,519 | 1,493 | 47% | 5,012

## Slide 22: Cost Breakdown
Chart: 
| 475.06.03.01 Panels | 475.06.03.02 Single Plane | 475.06.03.03 Gas Manifold | 475.06.03.04 Full Tracker Support and Assembly
Total | 917435.8622 | 243298.1712 | 1873135.4541 | 484809.0214
Chart: 
| L Labor | M Material | N Non-Fermi Labor
Total | 810753.5419 | 2055443.5594 | 652481.4076
Base Cost (AY K$)

## Slide 23: Quality of Estimate
Chart: 
| L1 Actual / M1 Existing P.O. | L4 / M4 Preliminary | L5 / M5 Conceptual | L7 / M7 Rough Estimate Pre-Conceptual - Uncommon Work
Total | 230917.1592 | 256075.9941 | 2937102.5888 | 94582.7668
Base Cost (AY K$)

## Slide 24: Labor & Material by FY
Chart: Annual Cost $K
| 42277 | 42643 | 43008 | 43373 | 43738
L Labor | 320197.6233 | 50644.5615 | 21702.6054 | 0 | 102513.6801
M Material | 174425.2226 | 66727.1513 | 1329140.8265 | 401501.9199 | 4637.1912
Non-Fermi Labor | 36814.3591 | 82148.8532 | 130570.6063 | 352657.869 | 44074.8799
Cumulative Total | 932358.3646 | 1131878.9306 | 2613292.9688 | 3367452.7577 | 3518678.5089
Base Cost (AY K$)

## Slide 25: Labor Resources by FY
Chart: Annual FTE's
| 42277 | 42643 | 43008 | 43373 | 43738
AD Administrative | 0.0278 | 0.0131 | 0.0485 | 0.0029 | 0
EN Engineering | 0.647 | 0 | 0.1019 | 0 | 0
ES Environmental, Safety & Health
FM Facilities Management
IT Information Technology
SC Scientific | 0.4041 | 0.3122 | 2.2735 | 3.2752 | 0.0528
TE Technical | 1.2667 | 0.9677 | 0.6485 | 2.6434 | 1.01
Cumulative | 2.3456 | 3.6386 | 6.711 | 12.6325 | 13.6953
FTEs by Discipline

## Slide 26: Summary
All groups are on-board with this work breakdown. We can make adjustments if needed as the work progresses.
York—straw terminations, vacuum leak tests, vacuum feedthroughs, possibly help with leak tests
Minnesota—CO2 leak tests, cut straws to length and terminate
Rice—insert straws and sense wires, complete panels
Houston—test all panels including HV tests in air and in gas, ensure that all channels see signals
Duke—procure straws, measure and document the locations of all sense wires and straws in each panel
Fermilab—leak test all panels, assemble panels into planes and planes into stations, construct full tracker
See Docdb4635 for more detail on university groups’ experience and facilities.