## Slide 1: Plan and Schedule of the MICE RF Modules
Soren Prestemon

## Slide 2: L3 milestones

## Slide 3: Plans for RF system design
Incorporate design improvements from this review
Perform vacuum calculations per review comments
Proceed with detailed design and specifications
Shoot for final vacuum vessel design review late March/early April

## Slide 4: RF Cavity preparation work
Proceeding well:
  Three cavities have been identified for Electropolishing
    selection based on inspection and frequency measurements
  EP setup is ready
  Should meet 2/17 milestone for cavity preparation readiness

## Slide 5: Key milestones moving forward
Delivery of two RFA modules to RAL: Mid-May 2016 (see MICE WBS)
  Full characterization tests of tuners after assembly
  RFA module assembly starts in the fall of 2015
  All hardware components ready by Oct. 2015
  RFA vessel fabrication readiness review: Mid-April 2015
  –RF coupler final review (experience from MTA): May 2015
  Cavity (with beryllium windows) selection and EP: Mid-June 2015
  Production of actuators: Starts March 2015