## Slide 1: MQXFA prototypes Structure and Plan
H. Felice, D. Cheng, S. Kincaid, S. Myers
G. Ambrosio, P. Ferracin

## Slide 2: Overview of the MQXF family Short and Long models and prototypes
 | LARP Short model MQXFS1/2 | LARP Short model MQXFS4 | LARP 1st prototype MQXFA01 | LARP Prototype MQXFA-02 and 3
Coil X-section design | v1 | v2 | v2 | v2
Coil Magnetic length RT/1.9 K (mm) | 1198/1194.4 | 1200/1196.4 | 4000/3988 | 4212.6/4200
Coil Physical length RT (mm) | 1510 | 1510 | 4312 | 4522.6
Structure (yoke) length RT (mm) | 1550 | 1550 | 4562.6 | 4562.6
From 1st to following prototypes:
    Different coil length
    Same structure length
A unique support structure is being designed

## Slide 3: Road Map of the MQXFA structure development
From MQXFS to MQXFA:
  Shell arrangement ( ½ segment in the end)
  Tooling cutouts and welding block cutouts dimensions
  Magnetic optimization
  CAD Baseline model v0
  Provide an accurate baseline model for BNL test facility
MQXFA specific
  Shell segment length optimization => ANSYS Analysis ongoing
  MQXFA01-02
    Yoke and pads: thick laminations
  MQXFA-03
    Structure optimization based on first prototypes results
    Yoke thin laminations => pending validation in short model
    LHe containment: stainless steel shell
MQXFA01 specific
  Coil longitudinal positioning optimization

## Slide 4: Road Map of the MQXFA structure development
From MQXFS to MQXFA:
  Shell arrangement ( ½ segment in the end)
  Tooling cutouts and welding block cutouts dimensions
  Magnetic optimization
  CAD Baseline model v0
  Provide an accurate baseline model for BNL test facility
MQXFA specific
  Shell segment length optimization => ANSYS Analysis ongoing
  MQXFA01-02
    Yoke and pads: thick laminations
  MQXFA-03
    Structure optimization based on first prototypes results
    Yoke thin laminations => pending validation in short model
    LHe containment: stainless steel shell
MQXFA01 specific
  Coil longitudinal positioning optimization

## Slide 5: Solid model
Baseline model of MQXFA01 (v0)
  Splice box (MQXFS)
  Endplate
    Bolts on return end
    Threaded endplate on lead end
    Buffer between endplate and splice box (45 mm) to be reduced for compatibility with CERN requirements
  Overall length: 4962.7 mm
  Weight ~ 7000 kg

## Slide 6: Baseline model v0 Based on v0
4563 mm
4962.7 mm
169.52 mm
230.18 mm
911.8 mm

## Slide 7: Consistency with Q1/Q3 CERN length requirements
From P. Fessia and H. Prin
Baseline v0 MQXFA dimensions consistent with Hi-Lumi LHC baseline
230.18 mm presently which can be reduced to 215.18
Presently 169.52 mm
In black box: cold dimensions
No box: warm dimensions

## Slide 8: Road Map of the MQXFA structure development
From MQXFS to MQXFA:
  Shell arrangement ( ½ segment in the end)
  Tooling cutouts and welding block cutouts dimensions
  Magnetic optimization
  CAD Baseline model v0
  Provide an accurate baseline model for BNL test facility
MQXFA specific
  Shell segment length optimization => ANSYS Analysis ongoing
  MQXFA-01-02
    Yoke and pads: thick laminations
  MQXFA-03
    Structure optimization based on first prototypes results
    Yoke thin laminations => pending validation in short model
    LHe containment: stainless steel shell
MQXFA01 specific
  Coil longitudinal positioning optimization

## Slide 9: ANSYS model status
In CAD Baseline v0:
  Preliminary ½ + 4 + ½ configuration
  Shell length: 911.8 mm
ANSYS 3D model is ready for detailed analysis
+ Extensive parametric study from Mariusz Juchno
Required optimization and study
  MQXFA: Structure segment length / number of segments
  Tolerance analysis
  MQXFA01: coil longitudinal position
    Aligned with lead end
    Centered with respect to the structure
    Decision based on
      Stress distribution
      Assembly (lead support…), field quality

## Slide 10: Road Map of the MQXFA structure development
From MQXFS to MQXFA:
  Shell arrangement ( ½ segment in the end)
  Tooling cutouts and welding block cutouts dimensions
  Magnetic optimization
  CAD Baseline model v0
  Provide an accurate baseline model for BNL test facility
MQXFA specific
  Shell segment length optimization => ANSYS Analysis ongoing
  MQXFA-01-02
    Yoke and pads: thick laminations
  MQXFA-03
    Structure optimization based on first prototypes results
    Yoke thin laminations => pending validation in short model
    LHe containment: stainless steel shell
MQXFA01 specific
  Coil longitudinal positioning optimization

## Slide 11: Proposal for Thin Lamination and LHe vessel implementation
MQXFD1 structure
Thick Lamination for yoke, collar and pad
FY15
FY16
FY17
May to Dec 2015
MQXFS1
Dec to April
2016
MQXFS1b
Coil replacement or preload adjustment
MQXFD0 structure
½ + 1 + ½ shell
MQXFSD2
Mech model
LARP
CERN
½ + 1 + ½ (2nd shell)
Yoke Thin lamination
x2?
MQXFSD3
Mech
model
Demonstration in short model between CERN and LARP
Implementation in long model/prototype
MQXFA02: LHe vessel ?
MQXFA03: thin lamination and LHe
June to October 2016
MQXFS2
LHe containment at FNAL
Thin lamination ?
MQXFA procurement
MQXFAD
mechanical model
Sept 2016 to May 2017
MQXFA01
June 2017
Feb 2018
MQXFA02
FY18
Jan 2018
Jul 2018
MQXFA03
MQXFS3
Using MQXFD2
Or MQXFD3
1 + 1 shell
MQXFSD0
Mech model
MQXFSD1
Mech model
½ + 1 + ½ shell

## Slide 12: Assembly and tooling preparation
Based on principle tested in MQXFD1 or to be tested in MQXFS1
  Yoke shell subassembly vertical => MQXFD1
    Tooling will be revised
  Coil assembly tooling
  Coil roll-over tooling
  Coilpack insertion
  Magnet lifting Tooling

## Slide 13: Coil-pack Insertion
Hydraulic actuators
Assembly master
Assembled coilpack
Pre-assembled master key in magnet

## Slide 14: Long structure specific tooling and assembly processes
Yoke shell sub-assembly performed on half magnet (2281 mm) vertically
Assembly of 2 sub-assemblies performed horizontally
  Model and design ongoing
Long coil pack assembly procedure to be defined

## Slide 15: MQXFL1 schedule
Assembly
Sept to Jan
4 coils ready
Drawings and RFQ
Mechanical Model
MQXFL1 ready end of 01/2017
Procurement
Structure on critical path
Way to speed up the process are investigated: instrumentation by vendors, start long lead items procurement asap after the review
MQXFA structure review 7/16/2015

## Slide 16: Summary
1st model MQXFA01 based on MQXFS
  Thick laminations for yoke
  Shell length to be optimized => ANSYS
  Preliminary CAD baseline v0 available
    Baseline for BNL test facility
    Consistent with CERN LHC Q1/Q3 length requirements
Proposal to implement
  LHe containment in the program
  Thin laminations
Joint effort with CERN
Schedule
  MQXFA structure review on July 16th 2015
  MQXFA01 ready for test at the end of January 2017
  Structure on critical path
    Possible ways to speed up the process being investigated