## Slide 1: Recent Magnet Results & Future Plans
Ambrosio & P. Ferracin
on behalf of the MQXF team
With special contributions by: R. Bossert, G. Chlachidze,
H. Felice, E. Holik, S. Izquierdo Bermudez, M. Juchno,
G.L. Sabbi, J. Schmalzle, M. Yu, …
HiLumi - LARP Collaboration Meeting
May 11-13, 2015
FNAL

## Slide 2: Outline
MQXF Design
Short Models (MQXFS)
    Status
    Results
Long Model & Prototypes (MQXFL & MQXFA/B)
    Status
Plans
Risks, Risk Mitigation & Opportunities
    HQ tests & coil analysis
Conclusions

## Slide 3: MQXF Design Finalization
Length & Gradient:
  Gradient: 132.6 T/m
  Length: 4.2 m (MQXFA), 7.15 m (MQXFB)
RRP strand specs: 108/127
  with 1.2 Cu/NonCu (632 A @12T, 331 A @ 15T 4.2K)
Cable keystone angle: 0.4 deg
Coil cross-section:
  Small adjustment
More margin
Better Quench Protection
Cost savings
OK for PIT conductor
For 2nd gen. cable
b6 optimization

## Slide 4: MQXF 2nd Generation Design
 | Unit | Value
Operating temperature | K | 1.9
Operating current | kA | 16.5
Peak field at op. current | T | 11.4
Op. overall current density | A/mm2 | 462
Stored energy/length | MJ/m | 1.17
Inductance/length | mH/m | 8.21
Peak field including strand self field
+125 µm Mid plane
-125 µm Pole
Δb6 = -5, Δb10=-0.5
-125 µm Mid plane
+125 µm Pole
Δb6 = +5, Δb10=+0.5

## Slide 5: Short Coil Fabrication Status
6 RRP coils by LARP:
  1 practice coil (cut for inspection & analysis)
  1 coil for test in mirror structure
  4 coils for MQXFS1/2 (2 need only instrumentation)
1 Cu, 1 low-grade, 3 RRP, 1 PIT by CERN:
  1 Cu and 1 low-grade Nb3Sn for practice
  1 RRP coil for possible single-coil test
  2 RRP coils for MQXFS1/2 (almost completed)
  1 PIT coil in progress
Mostly good coils,
a few bumps on the road,
more details tomorrow.
WG for MQXFS1 coil selection on Thursday

## Slide 6: Short Coil Fabrication QC
Electrical tests: Good
Dimensional tests: To be improved
  Some left-right asymmetry

## Slide 7: Short Coil QC (MQXFSM)
Mirror structure as coil test facility for QC:
  Load line within a few percent from MQXF load line
  Low prestress to avoid damage
Bolt on skin
Coil Protective Shell
Coil Midplane shim
Yoke (EDM’d blocks)
Aluminum Side Clamp
Design by
A. Zlobin & I. Novitski

## Slide 8: MQXFS1 Test Results - Preliminary
Chart: Quench #
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
MQXFSM1 @ 1.9K | 0.70325 | 0.75709 | 0.78277 | 0.79867 | 0.82184 | 0.82715 | 0 | 0.8281 | 0.84548 | 0.8451 | 0.85592 | 0.86656 | 0.85412 | 0.87434 | 0.87491 | 0.88825 | 0.89081 | 0.89471 | 0.89689 | 0.90197 | 0.89086 | 0.91332 | 0.907 | 0.90444 | 0.88896 | 0.90121 | 0.90121 | 0.90145 | 0.89898
16.5 kA
19.2 kA = 91% SSL
Conductor: RRP 108/127 by OST

## Slide 9: MQXFS1 Test Results - Preliminary
Ramp rate dependence & holding current tests
Chart: Ramp Rate (A/s)
| 5 | 14 | 50 | 100 | 200 | 400 | 300 | 500
 | 19162 | 19022 | 18671 | 18540 | 18362 | 17436 | 18107 | 16850
No quench in ramp down from 16.5 kA to 0 kA at 300 A/s
Note:
ramp rate dependence is different in mirror and in quadrupole
Holding 16.5 kA at 4.5 K for 2 hours w/o quench
To be repeated for longer time at 1.9 K
More details tomorrow morning in Magnet Session at 10:00 am
The new top-head for VMTF with current up to 30 kA at 1.9 K performed very well!

## Slide 10: Mech. Model & Short Models
Assembly & LN cooldown:
  1 mechanical model
  (15 cm long)
  2 short model structures with dummy coils
CERN
CERN
LARP

## Slide 11: Short Models & Mech Models
Strain gauge results:
consistent with FEM analysis
  Adjusting friction coefficients for fine tuning
More details tomorrow morning in Magnet Session at 10:00 am

## Slide 12: Long Models & Prototypes
LARP Status:
  Equipment:
    Wind&Cure @ FNAL just commissioned
    Wind&Cure @ BNL fabrication in FY16 (budget constrained)
    React&Impr @ FNAL operational
    React&Impr @ BNL operational (oven upgrade in FY16 for 4.2 m)
  Tooling:
    Wind&Cure ready for use
    React&Impr is being procured (one set in)
  4m coil fabrication is starting now; 4.2m coils start in 09/16
  Structure: review in mid July  procurement
  Vertical Test Facility upgrade @ BNL in progress
More details tomorrow afternoon in Magnet Session

## Slide 13: Prototypes
CERN Status:
  Equipment
    Modification of winding machine in progress, to be completed by 10/15
    Curing press operational
    Impregnation system to be delivered to CERN by 06/15
    Reaction oven to be delivered to CERN by 04/16
  Tooling
    Winding and curing tooling procurement launched, to be delivered in 11/15
    Reaction/impregnation tooling design in progress
  Coil fabrication to be started in 12/15
  Long support structure design started
More details tomorrow afternoon in Magnet Session

## Slide 14: Plans
Short model program: 5 CERN-LARP models, 2014-2017
  Coil fabrication started in 03/2014
  First coil test in 05/2015
  First magnet test (MQXFS1) in 08/2015 (2 LARP coils, 2 CERN coil)
Long prototype program: 2 (CERN) + 3 (LARP) models, 2015-2018
  Coil fabrication starts in 2015: 05 (LARP), 12 (CERN)
  First coil test in 07/2016 (LARP) and 08/2017 (CERN)
  First magnet test in 02/2017 (LARP) and 06/2018 (CERN)
Series production: 10 (CERN) + 10 (LARP) cold masses, 2018-2022
  Coil fabrication starts in 01/2018
  First magnet test in Q1/2020

## Slide 15: Risks & Mitigation Strategy
Assembly and pre-load of long coils with alignment features in long segmented structures
  Mitigation: short models have segmented structure
Quench Protection is challenging because of high energy density in the coils
  Mitigation: lower operating current wrt original design
  Mitigation: address QP through HQ tests
Field Quality: tradeoff btw turn compaction (for FQ) and room for expansion during HT (to avoid possible degradation and electrical issues)
  Mitigation: address FQ through HQ tests and coil analysis

## Slide 16
Recent HQ Test Results
HQ02b: fast training to 95% level with 200 MPa pre-load
01/15 HQ03a: first quench above operational level (80%)
Next: full training after removing 15 kA current limit
Small effect of high temperature quenches
G.L. Sabbi

## Slide 17
Magnetic Shim Test in HQ03
HQ03 Goal: maximum correction of b3 (+2.5 units) with no change in other harmonics
Note: shimming range is insufficient for simultaneous correction of b3, a3, b4, a4 in HQ03
Magnetic shimming plan and installation
Sextupole correction (15 kA)
+2.5
G.L. Sabbi

## Slide 18
Last HQ Plans before decommissioning
Next test (HQ03a-2) expected to be performed at Fermilab following the QXF mirror:
Complete training, evaluate performance; “partial” thermal cycle feedback
Include magnetic shims for correction of b3
Evaluation of new quench antenna and heater designs for application to QXF
Outlook beyond HQ03a-2:
Some indication of insufficient pre-load, to be confirmed in HQ03a-2
  Increase preload (HQ03b) ?
HQ03b goals:
  Check performance after pre-load increase
  CLIQ studies
  Timeline: October-November
  Location: CERN or Fermilab (if CLIQ upgrade is completed by then)
  Additional options: cycling test; quench limits (extend HQ02b); stress limits (HQ03c)
G.L. Sabbi

## Slide 19: Turn position  Field Quality
Chart: ZPositon (m)
| -0.5 | -0.45 | -0.4 | -0.35 | -0.3 | -0.25 | -0.2 | -0.15 | -0.1 | -0.05 | 0 | 0.05 | 0.1 | 0.15 | 0.2 | 0.25 | 0.3 | 0.35 | 0.4 | 0.45 | 0.5
B3 | -4.4728 | -38.4349 | -7.361 | 1.079 | 3.1434 | 4.1772 | 5.9304 | 7.6142 | 9.474 | 10.1426 | 9.3739 | 8.1817 | 6.5206 | 4.6236 | 3.6141 | 3.5991 | 7.6545 | 20.1031 | 50.2972 | 107.2333 | 25.8097
A3 | -0.36366 | -11.4908 | -5.7106 | -1.6893 | 0.34994 | 0.44887 | -0.50293 | -2.2782 | -3.4919 | -4.0653 | -3.5737 | -1.5433 | 0.83554 | 2.3061 | 2.0341 | 3.3008 | 10.9016 | 29.9487 | 73.0573 | 130.52 | 9.5211
Exploring correlation between turn position and field quality
Unallowed a3 and b3 Along Bore of HQ02
Cut HQ02 coils at locations corresponding to the magnetic measurements, compute field & compare with measurements
Coil Cuts
E. Holik
Notes: We are attempting to measure turn location of all 4 HQ02 coils with enough accuracy to correlate to the measured harmonics.

## Slide 20: Opportunities
Possible significant cost savings by using thin laminations
  Strategy: demonstrate it through short models
Possible cost savings by exchanging parts/components btw US-HiLumi & CERN
  Exploiting it in this phase
  Exploring continuation/increase in construction phase

## Slide 21: Conclusions
The Short Model program is going ahead at full speed generating good results
The Long Model/Prototype program is starting
We are addressing risks through design & plans
We are exploring how to exploit opportunities
Next big milestone:
MQXFS1 test this summer