## Slide 1: READINESS AND BOTTLENECKS FOR QXF MAGNETS
G. Ambrosio, P. Ferracin, E. Todesco
CERN, Geneva Switzerland
FNAL, LARP and HL LHC meeting
12th May 2015

## Slide 2: CONTENTS
Technical risks
Schedule risk

## Slide 3: TECHNICAL RISKS
Nearly all design features tested on HQ
  This is strongly reducing the risk of the QXF project
  Missing: adding the SS shell - to be done in 2nd or 3rd short QXF
Margin increased from 19% to 23%
  This gives some more relax on quench performance, quench protection, stress and prestress, … [see G. Ambrosio talk]
Recent decision of using 108/127, which is the strand layout mostly used by LARP [see P. Ferracin summary, A. Ghosh, B. Bordini]
  Risk and cost reduction
  CERN will produce short models with 132/169, than go to 108/127 for prototypes according to present plan
  108 gives twice amplitude flux jumps at low energy (variable thresholds for protection already in the baseline)

## Slide 4: SCHEDULE OUTLOOK
Color codes
  Orange: coil fabrication (excluding practice etc.)
  Light Green: horizontal test
  Light Blue: cold mass welding
  Deep Blue: cryostating
  Dark Green: horizontal test

## Slide 5: TECHNICAL RISKS: LENGTH
The length issue is the most critical
  LARP had three 3.4-m-long coils, CERN starts from scratch (or better from 11T 5.5-m-long coils that will come soon)
  First 4-m-long in LARP at the end of 2016
  First 7-m-long in CERN tested at the beginning of 2018
  Very short period between first and second long CERN prototype

## Slide 6: TECHNICAL RISKS: STRAND
It takes more than 1 year to order strand
  Test of the short can give feedback on the strand order for the series
  Test of the long cannot give feedback on the strand order for the series for CERN (and it is at the limit for US hilumi)

## Slide 7: TECHNICAL RISKS: LAMINATED STRUCTURE
We are considering a laminated structure for the iron yoke
  Two pieces, blue parts in the figure
  Allows a strong reduction of the cost (from 75 kchf/m to 30 kchf/m), so 7 M total
This will be tested on a short model (possibly 2nd or 3rd)
I think we should have this option tested on short on both sides of the ocean
  In principle one test is enough, but I think it is a risk to have a new long structure assembled for the first proto

## Slide 8: TECHNICAL RISKS: PROTECTION
Protection is still a major concern to me
  Outer layer quench heaters only do not provide adequate protection
  We are working with a very large Tmax (350 K)
Inner layer can be a viable option to provide redundancy and lower the hotspot
  Visual signs of degradation, but no evidence of longer delays
  [talk by G. Ambrosio]
  My favourite option since it is independent of the length – results will be available already with short models
CLIQ is an interesting technique [talk by E. Ravaioli]
  Codes are reliable , but final validation only with prototypes
Possibility of having the triplet on one circuit is being studied

## Slide 9: TECHNICAL RISKS: FIELD QUALITY
Iteration on the cross-section takes 1.5 years
  We just went to cross-section II (without testing yet the first one)
  But in this way we have midplane and pole shims allowing tune b6 over a wide range
    No change of cross-section is foreseen (unless major unexpected events)
  If b10 or b14 are a problem, we will add correctors and not change the cross-section
Magnetic shimming can take care of two large non allowed multipoles
  Corrects ±5 units of b3, ±5 units of a3, ±3 units of b4
  Only ±1 unit of a4
Evidence of large b5, a6, b7
  Difficult to act on these multipoles
  Consider increasing strength of correctors (b5, a6) or add correctors b7

## Slide 10: TECHNICAL RISKS: SCHEDULE
US Hilumi schedule was at the edge
  Last magnets ready for cryostat at the end 2023, plus preparation etc
  With one year slipping schedule looks more relaxed
    But no contingency, no failures accounted for
1.5 year between first test prototype and first winding of series coil

## Slide 11: TECHNICAL RISKS: SCHEDULE
CERN schedule more relaxed, but
  Only few months between test first prototype and first winding of the series coil (really too little)
  Assume a smooth series production for a 7-m-long coil (unrealistic)
  There is a considerable contingency (two years, with new schedule)

## Slide 12: CONTENTS
THANKS !