## Slide 1: PIP-II Systems Engineering and Integration
Don Mitchell
PIP-II Systems Engineering and Integration
9 March 2015

## Slide 2: Agenda
PIP-II Engineering Documentation
  Adherence to the FNAL Engineering Manual
  Documentation Requirements
  Functional Requirement Specifications
  Engineering Process Document Management (EPDM)
Concept to Operation – Next steps
Systems Integration

## Slide 3: PIP-II Engineering Documentation
  Adherence to the FNAL Engineering Manual
    Chapter 1 – Requirements and Specifications
    Chapter 2 – Engineering Risk Assessment
    Chapter 3 – Requirements and Specification Review
    Chapter 4 – System Design
    Chapter 5 – Engineering Design Review
    Chapter 6 – Procurement and Implementation
    Chapter 7 – Testing and Validation
    Chapter 8 – Release to Operations
    Chapter 9 – Final Documentation

## Slide 4: PIP-II Engineering Documentation
  Typical Documentation
    Request for Information
    Procurement Specification
    Technical Questionnaire
    Procurement Readiness Review
    Request for Proposal
    Vendor Proposal Review
    Vendor Selection
    Vendor Fabrication Review
    Material Certifications
    Documentation and Training Requirements
    Safety and Health Plan
    Fabrication Acceptance Test
    Performance Acceptance Test
    Installation Plan
    Safety Review(s)
    Commissioning Plan
    Operational Readiness Clearance
This list is not all-inclusive
    Functional and Technical requirements
    Statement of Work
    Risk Assessment
    ES&H and QA requirements
    Various reviews of all requirements
    Technical Design Report
    CAD models
    CAD drawings (electrical, mechanical, P&ID)
    Supporting Documents
    Engineering and design notes
    Design calculations
    Assembly and operating procedures
    Preliminary Design Review(s)
    Systems Integration Review(s)
    Final Design Review
    Procurement Plan
    Presentations

## Slide 5: PIP-II Documentation Requirements
  Required documentation is based upon the graded approach
    Subject to the results of the required Risk Assessment, the level of required documentation is determined.
    At the low end, the following documentation is required:
      Risk Assessment
      Functional Requirement Specification
      Preliminary Design Review
      Technical Design Report (recommended)
      Final Design Review
      Performance Acceptance Test
    The rigor applied at this level may be low
      Small review panels, maybe even one individual
      e-mails captured and put into the EDMS
      Informal reports
      All data is still captured and put into the EDMS

## Slide 6: PIP-II Documentation Requirements
  Required documentation is based upon the graded approach
    Subject to the results of the required Risk Assessment, the level of required documentation is determined.
    At the high end, the following documentation is also required:
      Statement of Work
      Project Management Plan
      Technical Requirement Specification
      Specification Review
      Systems Integration Review
      Up to 10 various Procurement documents
      Installation Plan
      Safety Review
      Commissioning Plan
      Operational Readiness Clearance Review
    The applied rigor at this level is stringent and formal

## Slide 7: PIP-II Documentation Requirements
  Required documentation is based upon the graded approach
    Subject to the results of the required Risk Assessment, the level of required documentation is determined.
    Additionally, supporting documentation is required such as:
      Calculations
      Purchase Orders
      Presentations
      Conference Posters
      Hazard Analysis
      FMEA (Failure Mode and Effects Analysis)
      Status reports
      Project Goals and Timelines
      Status of FTE and M&S for each Level 3 work activity
    This data is also maintained within the EDMS

## Slide 8: PIP-II Requirement Specifications
Extracts from the Technical Division Engineering Work Procedures Policy, TD-2300, released 9/5/2013
TIS: Technical Interface Specification
SOW: Statement of Work

## Slide 9: PIP-II Functional Requirement Specifications – Status
35 major systems currently have FRSs.
14 are released.
Focus has been on PXIE
Still needed:
  A PIP-II focus
  Power Supplies
  Infrastructure
  Small sub-systems
A FRS is not required until the design process begins.

## Slide 10: PIP-II Engineering Process Document Management

## Slide 12: PIP-II Engineering Process Document Management

## Slide 13: PIP-II Engineering Process Document Management

## Slide 14: PIP-II Engineering Process Document Management

## Slide 15: PIP-II Engineering Process Document Management
One storage location with global access
Integration of all CAD data with all Engineering documentation
Revision controlled
Always up-to-date
Provides easy access for all Users
Provides a consistent process
Well organized
Adherence to the intent of the Fermilab Engineering Manual
The PIP-II chosen EDMS solution is Teamcenter

## Slide 16: PIP-II Engineering Steps: From Concept to Operation
  Conduct a Risk Assessment
  Define the required documentation needed to complete the task
  Create a Functional Requirement Specification
  Begin the design process and supply all required documents
  Develop a Systems Integration Plan if needed
  Conduct Design Reviews and secure all approvals
  Develop a Procurement Plan
  Procure all components
  Assemble system components
  Test and validate the system
  Secure Operational Readiness Clearance if required
  Provide operations training
  Operate the system

## Slide 17: PIP-II Engineering Status
PIP-II is at various stages of the Product Lifecycle depending on the particular system
  PXIE (R&D Proof of Concept)
    LEBT: nearly fully commissioned, Testing and Validation
    RFQ: Fabrication phase
    MEBT: Fabrication, Procurement, ongoing Design
    HWR: Fabrication phase
    SSR1: Fabrication, Procurement, ongoing Design
    Power: Fabrication, Procurement, Design, Testing
    Controls & Instrumentation: Fabrication, Procurement, Design, Testing
  Facilities: Design phase within FESS
  SSR2: FRS has been created
  HB650 MHz cavity: Design phase, R&D fabrication
  LB650 MHz cavity: FRS has been created
2014
2015
2016
2017
2017
On-going
On-going

## Slide 18: PIP-II Systems Integration
Each system must be evaluated to identify any areas where multiple engineering disciplines overlap
  Electrical
  Mechanical
  SRF
  RF
  Water
  Pneumatic
  Instrumentation
  Micro-phonics
  Site Facilities
Where there are overlaps, an integration plan must be developed and engineered into a fully functional system
Many PIP-II components require a Technical Integration Specification, a Systems Integration Plan, and a Systems Integration Review

## Slide 19: Summary
The Fermilab Engineering Manual is used as a guide to the graded approach in identifying all required documentation.
Functional Requirement Specifications have been authored for nearly every major system. Many have been released.
PIP-II is at various stages of the Product Lifecycle depending on the particular system.
Our current focus in on the related R&D for PXIE.
PIP-II documentation is centrally located and organized by EPDMs within Teamcenter. This facilitates easy and direct access to all PIP-II documentation.
PIP-II engineers utilize an integrated design approach during the design process to minimize rework and schedule delays and to maximize system performance.
PIP-II is on schedule for concluding our R&D effort in 2018.