## Slide 1
Step IV Conceptual Design Studies: finished
Step IV Magnetic Shielding Detailed Engineering: finished
MICE Step IV Magnetic Shielding Fabricate Parts
MICE Final Step Conceptual Design ad Engineering
PRY Step IV
  cam concept to avoid overstressing of L-seal bolts (now ok up to 5 times calculated load)
  PRY legs arrived in UK, presently being installed
  Steve Plate in UK to oversee this
  Machining of PRY shielding plates ongoing as planned
  Draw-wire sensors arrived, will be shipped to UK shortly
PRY Final Step
  Required steel ordered
PRY Step IV: finish machining of PRY plates
Engineering/design of PRY Final Step
Transport of PRY to UK
Support installation
06 March 2015
1.05.03 MICE Magnetic Shielding
Holger Witte

## Slide 2
Step IV
Framework
PRY bases installed (UK)
One side of framework (south) in UK
Used for survey, shimming, … of north side before installed on south side
  Time savings
  MICE hall will be ready when PRY arrives
Schedule
  March 20: South plates in UK
  April 21: North framework + plates in UK

## Slide 3
PRY South Wall
South wall at Keller (March 5th)
  Trial assembly finished
Present status: dismantling
  Crating + shipping to JFK

## Slide 4: CAM Concept
Mitigates overstressing of L-Seal bolts
Stress analysis now ok up to 5 times calculated load on end plate of PRY
L-Seal

## Slide 5: RF Penetration
R150
Step IV PRY
Addition
for Step V’

## Slide 6: RF Penetration
5/10 Gauss Surface