## Slide 1: SSD Repair Plan
G.Velev
FNAL
Dec. 3rd, 2015

## Slide 2
Vladimir described the possible improvements discussed in the Magnet Systems Department (MSD)
I will present what is necessary to build SSD in TD (conceptual level)
I will discuss a possible magnet assembly plan, not repair (conceptual level)
  input from MSD engineers Steve Krave and Nikolai Andreev
All modifications are based on the assumption that the magnet must be assembled in the same vacuum vessel.
All estimates are preliminary.
Outline

## Slide 3: What we need …
Full 3D-drawings of the magnet
  The original procurement drawings are proprietary to Wang NMR
  The drawings do not represent the magnet as built
  The design should start from the magnet specs: fields, dimensions, etc.
  Full magnetic analysis is required
  Full FEA should be performed
  Include all modifications: e.g. new feedthrough modifications, lead stabilization, infrastructure for quench protection heaters, etc.

## Slide 4: What we need (cont’d.)
Production Tooling must be designed
    The bobbins are close to MRI type
    TD does not have any tooling which supports this type of winding
      Can improvise – an existing table (mounted horizontally)
        Slow rotation speed (1-2 turns per minute)
      Purchase a new winding stand ~$50-$60k, ~10-20 rpm

## Slide 5: FNAL Tooling - example

## Slide 6: Tooling for SSD
Support
Bobbin
Be creative and build a new bobbin rotating system,
tensioner exists

## Slide 7: Magnet “potting”
We agreed that the best option is to VPI the coils
  Conductor should be glass insulated (~2 mil) what we do for LCLS splittable quads, ~ $83k est. cost to insulate the cable.
  Need R&D
    A full-size END coil should be built
    Prefer it to be LHe tested - Fermilab does not have a facility to test this model

## Slide 8: SSD coil
62
layers

## Slide 9: Coil insulation
Polyester-glass fiber insulation sleeve, 1.5~2 mil
1.65x1 mm2
50 mm
For every layer of the Center coil, we need 60-80 mm more depending on the packing factor (or 40-50 turns)
At 784 turns per layer, we need 1-2 more layers
In radial direction, increasing the thickness will be compensated by removing layer-to-layer insulation

## Slide 10: VPI Tooling

## Slide 11: Conceptual Assembly Plan for SSD Magnet
Bobbin Preparation
  On arrival (after inspection) clean bobbin with alcohol.
  Apply release layer to bobbin to prevent stick-slip
  Apply G-10 ground wrap sheeting and side pieces ~0.5-1 mm.
  Remove rough spots in ground insulation.
  Wrap bobbin in 1 layer of fiberglass for epoxy wetting.

## Slide 12: Conceptual Assembly Plan for SSD - Winding
Coil Winding (EC2, SC, EC1, M2, M1) - each coil is the same, aside from # of turns
  Feed lead through lead in channel and fix it. Attach/solder the required (copper) stabilizer
  Wind 1st turn with 5 lb tension
  Wind 2nd turn with10 lb tension
  Wind 3rd turn and up with 17 lb tension
  Wind first 10 turns slowly ~1 rpm, gently tapping wire towards coil with Teflon tool to ensure tight packing
  Increase winding speed to comfortable rate (1-2 or 5-20 rpm)
  Layer jumps will occur by stuffing gap (less than cable width) with glass, then continue winding
  Attach/solder the required (copper) stabilizer for the lead(s) if needed.
  Tack outer lead into place with 5-minute epoxy and tuck out of the way
  Wrap 1 Layer of 50% overlap glass-tape ground insulation over coil. Tack as required with superglue.
  Install Heaters (~1/2” SS shim in Kapton sandwich)
  Wrap additional 50% overlap glass-tape ground insulation over heaters. Tack as required with superglue.

## Slide 13: SSD coil
48
28
56
20
62
layers

## Slide 14: Assembly Plan for SSD – VPI
Coil impregnation
  Mold release exposed bobbin and clamshells.
  Attach coil clamshells (~1/4” perforated half-coil SS sheets). Trim or shim as required.
  Fill remaining space with Nylon or Teflon epoxy filler.
  Install and seal outer impregnation shell. Install curing heaters on shell or inner bobbin.
  Bake in oven at 60°C for 48 hours before VPI.
  Impregnate with CTD-101k for 10-hour fill.
  Cure in place at atmospheric pressure.
  Remove shell and clean up coil.

## Slide 15: SSD coil

## Slide 16: Assembly Plan for SSD – Final
Coil Pre-stress System
  Install banding by wrapping coil with aluminum tape at ~ 50% of the yield stress (0.5*σy)
  Tack end of banding system to retain pre-stress.
Wire routing
  Route leads and heater leads as required.
  Route the instrumentation cables (voltage tabs, liquid level, etc.).
Shell Welding (very preliminary)
  Need a full design evaluation of the leads and feedthroughs
  Clean the half-shells for the helium vessel.
  Install half-shells for helium vessel and form the leads.
  Fix the leads.
  Weld and leak check.

## Slide 17: Production
In FY16-17, MSD is working on the flowing projects/programs: LCLS II, mu2e, g-2, Accelerator Support, Muon Beam Line (Muon campus), LBNF, LARP and HFM program.
Personnel:
  Magnet Design Engineer - difficult to estimate, but probably we will find MSD resources
  Mechanical Design Engineer (ANSYS, FEA) - difficult to estimate but probably we will find MSD resources
  Mechanical design/Production Engineer - we expect to have a person ~ FTE
  Drafters/Designers - TD does not have enough manpower (hire contractors)
  Technical personnel - ~2-3 contractors +1 existing experienced tech
  Procurement – we will need help, TD procurement is busy with LCLS II
  Technical Supervisor – OK
  Project Coordination – OK
  Physicist involvement - OK
Production space - IB2 can be used until FY18, maybe FY19 (depends on LARP and LBNF plans)

## Slide 18: Conclusion
If requested, TD/MSD can build the magnet(s)
We are not equipped for this type of solenoid, tooling is needed
The resources need to be secured
FEA analysis, full set of drawings and initial R&D are needed
The fully loaded cost ~ $1M without contingency and M&S
We do not see any shorter path with a high probability of success

## Slide 19: Backups

## Slide 20
Magnet Systems Department
G. Velev – Head
Deputy Head - Guram Chlachidze
H. Szuba
SC Magnet
A. Zlobin
V.V. Kashikhin
M. De Lima Lopes
E. Barzi
Measurements
& Analysis
S. Feher
G. Ambrosio
(G. Chlachidze)
L.Cooley
J. DiMarco
E. Holik
S. Stoynev
T. Strauss
Accelerator Support
G. Chlachidze
S. Baketz
T. Gardner
O. Kiemschies
A. Makarov
W. Robotham
(S. Krave)
Engineering-MD
V. Kashikhin
N. Andreev
R. Bossert
J. Carmichael
S. Krave
I.Novitski
Technical Support
S. Gould
J. Alvarez
S. Johnson
J. Karambis
R. Jones
S. Ransom (C)
E. Ruiz
L. Zimmerman
Fabrication
(O. Kiemschies)
M. Bossert
B. Galan
S. Johnson
L. Kaminskas
J. McQueary (C)
W. Ostrom
C. Pribyl
I. Samayavong
P. Sanchez
S. Sanchez
S. Sorenson
Systems and
Automation
L. Elementi
T. Thode
P. Dormann
Tooling
(O. Kiemschies)
D. Assell
R. Smith
Mu2e
M. Lamm
(S. Feher)
G. Ginther
H. Glass
A. Hocker
(V.V. Kashikhin)
(V. Lombardo)
(M. De Lima Lopes)
Mu2e Engineering
T. Page
J. Brandt
D. Evbota
D. Arnold
Y.Huang
(C. Orozco)
Strand and Cable Lab
D. Turrioni
V. Lombardo
P.Li (GS)
L. Yang (V)
A. Rusy
T. Van Raes
(M. Bossert)
SCM Fabrication
A. Nobrega
(J. Carmichael)
(D. Evbota)
(S. Krave)
C. Orozco
C. Santini
M. Yu
R. Kucharski
L2,L3,L4 project
leaders

## Slide 21: Basic Coil parameters

## Slide 22: Cost estimation
Part 1: Engineering Analysis of improvements to known/potential issues |  |  |  |  |  |  |  | 
 | Two months of effort for engineering analysis: |  |  |  |  |  |  | 
 | - Analysis of conductor and bandage tension in operation |  |  |  |  |  |  | 
 | - Stabilized conductor for feed-throughs |  |  |  |  |  |  | 
 | - Increase E2 windings? |  |  |  |  |  |  | 
 | - Method of pre-load rings: weld; gap filled with epoxy |  |  |  |  |  |  | 
 | - Amount to increase AL bobbin thickness/side-wall |  |  |  |  |  |  | 
 |  |  |  | $/hr | Hours | Total |  | 
 |  | Physicist |  | $200.00 | 60 | $12,000 |  | 
 |  | Mechanical Engineer |  | $160.00 | 120 | $19,200 |  | 
 |  | Magnet Designer |  | $200.00 | 120 | $19,200 |  | 
 | Total Estimate |  |  |  |  | $50,400 |  | 
Part 2: Mock-up coil winding: |  |  |  |  |  |  |  | 
 | Three months of effort to engineer, design, analyze, procure, fabricate and QA three Mock-Up coils (2 small and 1 longitudinally scaled). Includes: Mech analysis; design; procurement; wind & pot; test; section |  |  |  |  |  |  | 
 |  |  |  | $/hr | Hours | Total |  | 
 |  | Physicist |  | $200.00 | 80 | $16,000 |  | 
 |  | Mechanical Engineer |  | $160.00 | 140 | $22,400 |  | 
 |  | Electrical Engineer |  | $160.00 | 80 | $12,800 |  | 
 |  | Drafter |  | $85.00 | 80 | $6,800 |  | 
 |  | Procurement |  | $95.00 | 40 | $3,800 |  | 
 |  | Inspection |  | $95.00 | 24 | $2,280 |  | 
 |  | Supervision |  | $110.00 | 24 | $2,640 |  | 
 |  | Technician |  | $85.00 | 280 | $23,800 |  | 
 |  | Project Coordination |  | $95.00 | 12 | $1,140 |  | 
 | Total Estimate |  |  |  |  | $91,660 |  | 

## Slide 23
Part 3: The coils on the bobbin |  |  |  |  |  |  |  | 
 | Eight months of effort to engineer, design, analyze, procure, fabricate and QA one Coil Form with heaters plus required tooling (wind & pot) |  |  |  |  |  |  | 
 |  |  |  | $/hr | Hours | Total |  | 
 |  | Physicist |  | $200.00 | 100 | $20,000 |  | 
 |  | Mechanical Engineer |  | $160.00 | 600 | $96,000 |  | 
 |  | Electrical Engineer |  | $160.00 | 160 | $25,600 |  | 
 |  | Drafter |  | $85.00 | 320 | $27,200 |  | 
 |  | Process Engineer |  | $85.00 | 240 | $20,400 |  | 
 |  | Data Management |  | $95.00 | 80 | $7,600 |  | 
 |  | Procurement |  | $95.00 | 120 | $11,400 |  | 
 |  | Inspection |  | $95.00 | 80 | $7,600 |  | 
 |  | Supervision |  | $110.00 | 80 | $8,800 |  | 
 |  | Technician |  | $85.00 | 1200 | $102,000 |  | 
 |  | Project Coordination |  | $95.00 | 120 | $11,400 |  | 
 | Total Estimate |  |  |  |  | $338,000 |  | 
Part 4: The LHe Vessel and Final Assembly |  |  |  |  |  |  |  | 
 | Eight months of effort to engineer, design, analyze, procure, fabricate and test one LHe Vessel (pressure vessel) AND install Coil Form |  |  |  |  |  |  | 
 |  |  |  | $/hr | Hours | Total |  | 
 |  | Physicist |  | $200.00 | 120 | $24,000 |  | 
 |  | Mechanical Engineer |  | $160.00 | 600 | $96,000 |  | 
 |  | Electrical Engineer |  | $160.00 | 120 | $19,200 |  | 
 |  | Drafter |  | $85.00 | 250 | $21,250 |  | 
 |  | Process Engineer |  | $85.00 | 160 | $13,600 |  | 
 |  | Data Management |  | $95.00 | 40 | $3,800 |  | 
 |  | Procurement |  | $95.00 | 160 | $15,200 |  | 
 |  | Inspection |  | $95.00 | 80 | $7,600 |  | 
 |  | Supervision |  | $110.00 | 80 | $8,800 |  | 
 |  | Technician |  | $85.00 | 800 | $68,000 |  | 
 |  | Project Coordination |  | $95.00 | 40 | $3,800 |  | 
 | Total Estimate |  |  |  |  | $281,250 |  |