## Slide 1: Status of the PD-SP Detector Support Structure (DSS)
Gina Rameika
LBNC Meeting
June 22 – 24, 2017

## Slide 2: Detector Support Structure

## Slide 3: Design and Analysis Complete : DocDB#3339
This body of work has take 80% of my effort since April 24

## Slide 5
Drawings by 2 engineers at PSL
Calculations by 2 engineers at ANL
Review by 1 additional FNAL scientist

## Slide 6: The concept
8 Beams :
3 Runway
5 Bridge
3 support detector elements
2 just installation
9 Support Assemblies which penetrate the cryostat and are supported by the cryostat warm structure

## Slide 7: Support Tube Assembly : Top and Bottom

## Slide 8: Support Tube and Support Rod

## Slide 9: Link rod assembly attaches to the Runway Beam

## Slide 10: Bridge beams move along Runway beams via trolleys

## Slide 11: Detector elements are positioned on Bridge beams via trolleys

## Slide 14: Procurement Status
Beams :
  fabricated in Switzerland
  To be delivered by end of June
  Support Assemblies :
  Support Tube Assembly procured by CERN (company in Spain)
  Support Rod Assembly :
  40 separate procurements by PSL
  Many parts received.
  Awaiting : Rod weldment 6/29

## Slide 15: 4/7 Support Tube Weldments at EHN1

## Slide 16
DSS Feedthrough port on
cryostat

## Slide 17: Next Steps
Assemble a single Support Rod Assembly at PSL
Package parts IKEA style and ship to CERN
Develop assembly procedures
Develop installation procedures
Assemble and install
PSL engineer will be at CERN week of July 4 or 11 to oversee and assist with assembly
At the present time there is no reason to believe that the DDS won’t be ready in time to be installed when the cryostat is ready for it.