## Slide 1
Steve Holmes
PIP-II Risk Workshop
6-7 April 2017
Assumptions and Enterprise Risks

## Slide 2: Assumptions that relate to Risk/Funding
The DOE/OHEP will provide budget authority in line with the anticipated funding profile as shown below in $M. This profile represents the profile contained in the Mission Need Statement, modified to reflect the actual budget authority received in FY17. It is anticipated that a revised profile will be available following the President’s FY18 Budget Request.
Escalation rates are determined by each DOE laboratory budget office, and are documented in the table below.
Long-lead procurements will be authorized via CD-3a coincident with establishment of the project baseline at CD-2. Long-lead procurements will include advanced purchases of Nb, initial superconducting cavity orders, and initiation of site preparation activities.

## Slide 3: Assumptions that relate to Risk/International Partners
India is strongly engaged with Fermilab in the R&D phase of PIP-II, and will make a significant in-kind contribution to the PIP-II construction phase. The scope of work for the R&D phase is described in the “Joint Project Document for the R&D Phase of the Indian Institutions and Fermilab Collaboration”. It is assumed that the deliverable dates in this document will be met.
Agreements on in-kind contributions from international partners to the PIP-II construction phase will be formalized by the time of CD-2.
The scope of in-kind contributions assigned to India/DAE and other international partners for the construction phase will only be formalized by the time of CD-2. However, planning for the construction phase currently assumes the following scope for in-kind hardware contributions.
The deliverable schedules for international in-kind contributions to the construction phase will be formalized by the time of CD-3.
The project will not hold any cost contingency associated with in-kind contributions from international partners. The schedule risk associated with in-kind contributions will be identified in the PIP-II Risk Registry. Risks associated with finalizing international agreements to support the Project are held by the DOE Program Office.
Possible consequences of non-conformance with standards of in-kind contributions will be captured in the PIP-II risk register.

## Slide 4: Assumptions that relate to Risk/ESHQ
The NEPA process will be complete by June 2018, in advance of CD-2.

## Slide 5: Assumptions that relate to Risk/External Activities
Installation and commissioning of new systems required for injection of 800-MeV protons into the Booster will be scheduled coincident with the interruption to accelerator operations in the Main Injector complex required for integration of the long baseline neutrino facility (LBNF). This interruption is currently anticipated as lasting 21 months, with a start date of Q3FY24 .

## Slide 6: Assumptions that relate to Risk/Access to Resources
Access to SRF infrastructure will be available and operable during the remainder of the R&D phase and throughout production as necessary to maintain schedule. In particular:
  SRF Processing: cleanrooms, chemical facilities (ANL and FNAL)
  Performance testing: VTS, HTS, STC, CMTF
  Liquid Helium availability: Cryogenics at MDB, VTA, CMTF

## Slide 7: Assumptions that relate to Risk/Conventional Facilities
1,400 gallons per minute of industrial cooling water (ICW) will be available for PIP-II process loads. This flow will be available in all operating conditions. The connection location from the existing site-wide ICW will be in the vicinity of AZero;
ICW will be utilized for Fire Protection. The connection location will be in the vicinity of AZero;
The PIP-II ICW return discharge will be routed to the existing AZero cooling pond. It is assumed that the existing system to pump the ICW to the Casey’s Pond system is adequate for this flow.
250 tons of chilled water will be available from the Central Utility Building (CUB) for use by PIP-II. The connection point for the chilled water will be in the vicinity of CUB;
Existing feeder 46A, fed from the Kautz Road Substation, will be used for backup of critical PIP-II systems;
Existing electrical ductbanks will be utilized for PIP-II feeders from MSS to manhole P-71 in the main ring;

## Slide 8: Assumptions that relate to Risk/Technical Performance
To the extent possible, the PIP-II Injector Test (PIP2IT) being developed as part of the R&D phase will be relocated to form the front end of the PIP-II linac once the required conventional facilities are available.

## Slide 9: Assumptions that relate to Risk/Transition to Operations
Operating funds will be available to support maintenance and operations of PIP2IT systems once commissioning of each system is completed.
Operating funds will be available to support maintenance and operations of the 800-MeV linac, Booster, Recycler, and Main Injector once Key Performance Parameters (KPPs) associated with each of these systems is achieved.
Operating funds (special process spares) will be available to support the fabrication of an initial complement of spare components.

## Slide 10: Enterprise Risks
Failure to reach agreement on international in-kind contributions
Delay in formalizing international in-kind contributions
Assumed construction (post-CD-3) funding profile not achieved
Delay in access to SRF testing and fabrication infrastructure
Major accident/incident on the Fermilab site
Cryoplant delivery delay