## Slide 1: International Collaborations for PIP-II: R&D and Construction
Shekhar Mishra
PIP-II Machine Advisory Committee
March 15-17, 2016
Fermilab

## Slide 2: Outline
Charge
  Is the program, and division of responsibilities, outlined in the Joint R&D Project document well aligned with the needs of PIP-II
  Will it support a construction start encompassing both U.S. and Indian deliverables?
Indian Institutions and Fermilab Collaboration on R&D
  Areas of R&D Collaboration
  Technical Progress
  R&D Phase Summary
DAE-DOE Discovery Science Agreement Project Annex I
  Indian Strategy on PIP-II
  Project Annex I: Areas of Collaboration
  Project Annex I: PIP-II Construction deliverables
Summary

## Slide 3: IIFC: Joint R&D
A DAE-DOE Joint Project Document for the R&D Phase of IIFC was signed in Aug 2015.
Goals:
  Jointly Retire all the critical R&D by end of CY2018
    Cover each major component of SRF Linac downstream of HWR.
  Develop infrastructure and industries for the PIP-II construction phase In-Kind Contributions.
Development and test of SSR1 Cryomodule with beam at PXIE
  Deliverables from India
    2 SSR1 Dressed Cavities, CM Design
    8, 325 MHz 7 kWatt Solid State RF Amplifiers System
    RF Protection Interlock and LLRF
Development and Test of one HB650 MHz Cryomodule
  Deliverables from India
    3 HB650 Dressed Cavities
    Horizontal Test Stand
    8, 650 MHz 40 kWatt Solid State RF Amplifiers System
    RF Protection Interlock and LLRF
Development LB650 Dressed Cavities.
Development of SSR2 Cavities.

## Slide 4: IIFC Technical Management
Sub-Project | Indian-DAE Sub-Project Coordinator | Fermilab Sub-Project Manager
Accelerator Physics | S. Krishnagopal, BARC | Valeri Lebedev
Ion Source | P. Roychowdhary, BARC | Alexander Shemyakin
RFQ | S V L S Rao, BARC | Alexander Shemyakin
LEBT/MEBT (Magnets) | Sanjay Malhotra, BARC | Stoyan E. Stoynev
Beam Dump | Jose V Matthew, BARC | Alexander Shemyakin
SSR1 Cavity Design | P. N. Prakash, IUAC | Leonardo Ristori
SSR2 Cavity Design | S. Krishnagopal, BARC | Leonardo Ristori
SSR1 + SSR2 Cavity Manufacture | Vinay Mishra, BARC | Leonardo Ristori
SSR Cryomodule | Vinay Mishra, BARC | Leonardo Ristori
650 MHz, b = 0.61 Dressed Cavity | Sumit Som, VECC | Tom Nicol
650 Mhz, b = 0.92 Dressed Cavity | Avinash Puntambekar, RRCAT | Tom Nicol
650 MHz Cryomodule | Prashant Khare, RRCAT | Tom Nicol
Instrumentation | Gopal Joshi, BARC | V. Scarpine
Accelerator Controls | Gopal Joshi, BARC | J. Patrick
Solid State RF 325 MHz | Manjiri Pande, BARC | Ralph Pasquinelli
Solid State RF 650 MHz | Mahendra Lad, RRCAT | Ralph Pasquinelli
325 MHz RF Coupler | Rajesh Kumar, BARC | Leonardo Ristori
650 MHz RF Coupler | Rajesh Kumar, BARC | Tom Nicol
RF Protection Interlock | Gopal Joshi, BARC | Peter Prieto
Low Level RF | Gopal Joshi, BARC | Brian Chase
Cryogenic Plant and Distribution | Mukesh Goel, BARC | Arkadiy Klebaner
SRF Infrastructure | Satish Joshi, RRCAT | Allan Rowe
Vertical Test Stand | Satish Joshi, RRCAT | Alex Melnychuk
Horizontal Test Stand | Pradeep Kush, RRCAT | Joe Ozelis
HTS-2 Control Electronics | Pravin Fatnani, RRCAT | Joe Ozelils
650 MHz Cryomodule Test Stand | Vinay Mishra, BARC | Mike White
Team Center/Database | C S R Murthy, BARC | Tony Metz
We have planned quarterly face to face meeting in India with Technical managers. Where a minimum of 2 Fermilab L3 and Shekhar Mishra are expected to participate.

## Slide 5: IIFC: MEBT Dipole and Quadrupole
BARC is designing and fabricating:
  Dipole and Quadrupole for MEBT
  Solenoid for SSR2
  Warm Magnets for the 650 MHz Section of SRF Linac

## Slide 6: IIFC: b = 0.22 R&D: IUAC, BARC and FNAL
Two SSR1 cavities were received from IUAC,
Chemically processed at ANL and cold-tested at Fermilab
  IUAC fabricated cavity meets the PIP-II specifications
Cavities will be dressed at IUAC/BARC

## Slide 7: IIFC: b = 0.47: BARC, IUAC and FNAL
Fermilab has worked on SSR2 RF Design.
BARC has initiated to expand on this SSR2 design and will fabricate 1st prototype.
  Nb to be provided by Fermilab
BARC Investigating details of cavity design, fabrication, including e-beam facility
E
M

## Slide 8: IIFC: Development of b = 0.61, 1-cell Nb cavity VECC
VECC has fabricated one b = 0.61, 1-cell Nb cavity in collaboration with IUAC. ( Dec 2015)
Processing and testing at Fermilab (3/2016)
Half cells after cleaning
1-cell cavity under fabrication
Cavity half cells being put inside EBW machine for Equator welding
VNA testing of single cell cavity
Vacuum leak rate checking of single cell cavity at LN2 temperature

## Slide 9: IIFC: Design Development of b = 0.61, 650 MHz cavity VECC
5-cell LB650 cavity design carried out, using new FRS.
  The necessary parameters are well within the prescribed limits .
The design studies includes
  3D Multipacting
  Lorentz Force Detuning (LFD)
  Pressure sensitivity under external liquid helium pressure
  Structural analysis with Stiffener Rings
Further study is in progress for finalizing the design.
  It will include the Fermilab End Group and He Vessel design.
Stiffening Ring

## Slide 10: IIFC: Status of 650 MHz single-cell cavity (RRCAT)
RRCAT/IUAC Fabricated one Nb HB650 650 MHz single-cell cavity (July 2013).
  Processed & tested at Fermilab
  The cavity achieved Eacc 19.3 MV/m with Q > 4E10 at 2K.
Cavity VTS mounting
Q0 vs Eacc plot of Cavity

## Slide 11: IIFC: Progress on HB650 cavity (RRCAT)
In October 2013, 650 MHz cavity beta was changed from 0.9 to 0.92 to improve the cavity performance at high current.
HB650 (=0.92) five-cell cavity development at RRCAT
  New set of forming tools for =0.92 five-cell cavity have been made.
  Initial half-cell forming on copper and niobium has been carried out.
High RRR niobium sheets procured will be used for 1st five-cell cavity.
  Nb-Ti and Ti procured earlier can not be used for =0.92 cavity due to change in dimensions.
Development of various fixtures has been taken up after final design of HB650 cavity released from Fermilab on 2/10/2016.
HB650 (=0.92) forming tool and formed half-cell

## Slide 12: Tuner and Helium Vessel for HB Cavity
Helium Vessel with Auxiliaries and Supported by Bellow Restrain
Tuner Stiffness ~ 68 kN/mm
End Lever Tuner

## Slide 13: IIFC: 650 Cryomodule Design (FNAL and RRCAT)
Design of cryomodule for 650 MHz, β = 0.92 SCRF cavity is under progress.
  One cryomodule contains six cavities and no magnet
  Cryomodule is standalone unit
Major design activities with regard to major subsystems of cryomodule are
  Preliminary design almost complete
    Vacuum vessel
    Thermal shield
  Design for following subsystems is to be start
    Strong back support
    Cryogenic Flow distribution
    Cooldown piping system

## Slide 14: DAE: 7 kW, 325 MHz SSRFPA (BARC)
RF Power
Waveform at 7 kW on spectrum analyzer
Display of Calorimetric measurement of RF Power
Sensor data of Calorimetric measurement of RF Power
Meets the Design Specifications

## Slide 15: IIFC: Test of 3 kW at 325 MHz amplifier @ Fermilab
Chart: 3 kW, 325 MHz Amplifier endurance test ( 210 Hours continuously) at Fermilab
Time (Hrs) day wise
RF power
Ambient Temp. variation
Power: 3 kW
Overall Gain: > 65 dB
Efficiency : 65 %
Spurious noise:<- 70 dBc
3 kW RF Amplifier

## Slide 16: DAE: Progress on 650 MHz RF Power (RRCAT)
225 kW, 505.8 MHz solid state RF power amplifier system has been, indigenously developed and deployed in 2.5 GeV/200 mA Indus-2.
30 kW, 650 MHz RF power amplifier, design and development work was initiated based on draft FRS received in Dec 2010 from Fermilab.
500 W Amplifier module
Operating frequency: 650 MHz
Output Power: 500W (CW)
Gain: 21 dB
Bias Voltage: 50 V DC
Drain Efficiency: > 67%
Input/Output: N type connector
Cooling: Water Cooled

## Slide 17
DAE: Progress – 650 MHz RF Power (RRCAT)
17
Assembled 15 kW Amplifier of size (1m*1.2m*2m)
Testing of 30 kW amplifier with dummy load
Interface issues:
Interfacing with other systems are under discussion need documentation and agreed upon before proceeding with fabrication of SSRA

## Slide 18: IIFC: RF Protection Interlock System (BARC and FNAL)
Fermilab shared the RF Protection Interlock (RFPI) System details to BARC in early 2013.
The specifications for the Next generation RFPI system were Jointly Developed by Fermilab and BARC
The Next Generation RFPI system has been designed and fabricated at ACnD/BARC. The functional testing has also been done.
The RFPI system will be tested at Fermilab soon
For extensive testing of RFPI at BARC
  Fermilab will send One SSR1 cavity and Cold Section of Coupler.
  Warm part of the coupler and interface to RF etc. can be fabricated at BARC based on Fermilab drawings.
Five RFPI units have been fabricated at BARC
  Shipment awaits modified plan of testing

## Slide 19: IIFC: RFPI System under test at BARC
A complete redesign of the Fermilab RF Protection Interlock system has been done in collaboration with BARC.
BARC has completed detail test
  It will be tested at Fermilab at HTS-1 this summer.

## Slide 20: IIFC: Scope of the PIP-II LLRF system (Fermilab and BARC)
Fermilab has shared the existing and operational design of the LLRF system with BARC.
  Fermilab and BARC are Jointly working to upgrade the current system.
Low Lever Radio Frequency System is required to control the RF power being injected into a cavity. LLRF system consists of
  A high precision Master Oscillator and Phase Reference lines supporting multiple frequencies
  Local Oscillator generation and distribution
  Low Level RF Control Stations to precisely regulate up to 4 SRF cavities’ RF vector and resonant frequency, microphonics and Lorentz Force Detuning
  Interface with Timing, Machine Protection, Instrumentation and Controls
  Diagnostic and control software

## Slide 21: IIFC: Work Plan (Fermilab and BARC)
Fermilab shared the LLRF details with BARC in November 2015.
  FRS, TRS and interface documents are being finalized
The changes in the design will be carried out at BARC based on the testing at Fermilab
The design for next generation LLRF system will be done jointly by Fermilab and BARC.
  VHDL codes, Software and firmware for SoC based digital LLRF module and resonance control module
  EPICS and GUI development
BARC will supply prototype boards for a development system for testing and software development at BARC and Fermilab
  Mirror test systems
Final boards will be fabricated by BARC based on testing

## Slide 22: IIFC: 650 MHz Dressed Cavity Horizontal Test Stand
FNAL
RRCAT
Two 40 kWatt Units
(RRCAT)
IIFC RF Protection
(FNAL/BARC)
LLRF
(FNAL/BARC)
Integration and Controls (FNAL/BARC)
Q3/4-CY16
Cryostat at Fermilab May 2017
Cryogenics for HTS July 2017
Two 40kWatt RF July 2017
LLRF/RF Protection July 2017
Control System May 2017
Integration with cryostat Oct 2017
Test of 1st Dressed Cavity Dec 2017
FNAL
FNAL
Cryogenics and its Controls

## Slide 23: IIFC: System Test of SSR1 CM and RF Power with Beam
FNAL
FNAL
FNAL
FNAL
IIFC/ FNAL
IIFC/FNAL
Magnet
Magnet
Magnet
Magnet
10 MeV Beam PXIE
FNAL
IIFC RF Protection
(FNAL/BARC)
IIFC LLRF
(FNAL/BARC)
Integration and Controls (FNAL/BARC)
7 kWatt
(BARC)
7 kWatt
(BARC)
7 kWatt
(BARC)
7 kWatt
(BARC)
7 kWatt
(BARC)
7 kWatt
(BARC)
7 kWatt
(BARC)
7 kWatt
(BARC)
Cryogenics
(FNAL)
Instrumentation
(FNAL)
Axillary Systems
(FNAL)
Q3-CY2018
With Beam
FNAL
FNAL
SSR1 CM May 2017
Solid State RF Jan 2018
LLRF/RF Protection Jan 2018
Control System Jan 2018
Cryogenic for SSR1 Jan 2018
Integration with CM July 2018
(completion dates shown)
FNAL
FNAL
FNAL
FNAL
FNAL
FNAL
FNAL
FNAL

## Slide 24: IIFC: Integrated Test of HB650 Cryomodule and RF Power
IIFC RF Protection (FNAL/BARC)
IIFC LLRF
(FNAL/BARC)
Integration and Controls (FNAL/BARC)
40 kWatt
(RRCAT)
Cryogenics
(FNAL)
Instrumentation
(FNAL)
Axillary Systems
(FNAL)
FNAL
FNAL
FNAL
IIFC
IIFC
IIFC
40 kWatt
(RRCAT)
40 kWatt
(RRCAT)
40 kWatt
(RRCAT)
40 kWatt
(RRCAT)
40 kWatt
(RRCAT)
Cryogenic Distribution Box IIFC
Q4-CY2018
CM Cold
With RF
Solid State RF April 2018
LLRF/RF Protection April 2018
Control System April 2018 Cryogenic for April 2018
Integration without CM July 2018
HB650 CM Sept 2018
FNAL
FNAL
FNAL
FNAL
FNAL
FNAL

## Slide 25: PIP-II Construction Deliverables: India
A model for the In-Kind Contribution has been developed and presented to both DAE and DOE.
  Formal agreement pending review of the R&D Phase
Dressed High Power Tested Cavities (50%)
  SSR2
  LB650
  HB650
SSR2 Solenoid Magnets (100%)
650 Warm Magnets (100%)
Solid State RF Amplifiers at 325 and 650 MHz at various power (100%)
Cryogenic Plant (one)
LLRF and RF Protection System
BPM and BLM
Control

## Slide 26: Summary
International Collaboration is vital for the timely execution of the PIP-II.
  PIP-II is absolutely needed for the 1.2 MW running of DUNE.
With India, Fermilab is working on R&D topics that spans the whole SRF accelerator.
  These R&D should conclude by the end of CY18.
    Which would retire all the critical PIP-II R&D.
The construction deliverables are defined in the Joint Project Annex I Document
  In CY17-18, Fermilab, DOE and DAE will decided on the final construction deliverable table for PIP-II.
Fermilab and DOE are also working to develop collaborative programs with UK, France and Italy