## Slide 1: Run II Upgrade
H.Weerts
Argonne National Laboratory
DØ special Collaboration meeting
Fermilab
June 10, 2014
Anec: Boaz

## Slide 2: Introduction
Remarkable occasion:
Not given DØ talk for ~10 years, except D0 France
Used to give at least one/week
There is live after DØ, but how much…….
This really has little to do with science, it is simply history.
Amazing how much I forgot……..
Amazing that some things came back and I remembered them.
(except how things are accomplished)
RelearnØ

## Slide 3: Talk outline and plan
Run IIA upgrade activities 1996/7-2001
Try to be objective, but it is a personal view
Try to do it in a historical order
During 1990’s collaboration also transformed itself, grew and became more international  J.Womersley talk

## Slide 4: Upgrade
Lehman review March 1997
First Lehman review I was involved in as spokes
Introduction talk at our baseline review. Why me ?

## Slide 5: Upgrade
Lehman review March 1997
Run I

## Slide 6
Upgrade
Lehman review March 1997
Run I
Run IIa
Upgrades:
Momentum measurement
Vertex tagging
Better muon system
Trigger capabilities
Electronics for crossing time ; 2.4msec-> 396 nsec -> 132nsec
Shielding

## Slide 7: Upgrade; what was it?
Lehman review March 1997

## Slide 8: Upgrade
Lehman review March 1997
Not part of Upgrade, but large effort:
Upgrade of offline computing with changes to hardware, object oriented approach & first non-FNAL farms
Later talk

## Slide 9: Upgrade
Lehman review March 1997
Request base-lining of project.
Upgrade Project was base-lined i.e. construction funds available and start construction in a Jan 1998 review
Estimated time:
01 Oct 1999
29 Nov 1999
Ready to roll in:
Rolled & hooked up:

## Slide 10: The Upgrade management
Jim Christenson
Mike Tuts
Hard to find pictures

## Slide 11: Upgrade cost
Concerns at Lehman review March 1997.
Total capital cost: $60,659K in FY95$
Need to be specific a la Tuts
Special Slide by J.Christenson
DoE funding $3M short
Meeting Collider Schedule requires funding earlier then available from DoE
Have secured funds needed for this , but concerned about future years
Have identified $1.8M
Exploring other sources…….
Collaborating Institutions have pledged ~$1.9M prefunding for FY97; additional $1M for FY98
?
(upgrade $39M + Solenoid, Project support, G&A: $21M)
HM & HW charged to find missing funds
Does not work
Lehman review March 1997

## Slide 12: D0 workshop 1997, Indiana Univ.
Let pictures speak for themselves
No idea what we were in for………..
(Only picture of JC I could find)
A lot of activities at Fermilab, universities and institutions worldwide; R&D ongoing; fabrication & production lines ramping up

## Slide 13: Upgrade
~April 1999
(~ 1.5 years after baseline)
Concerns about how upgrade was progressing from DoE and others.
Rollin date had been moved to May 2000, considered not realistic
Good progress after March 1997 review for 1998……..
Jim Christenson resigned as Upgrade Project Manager (April 1999)
Great upheaval in upgrade project and in collaboration.
Reorganization of upgrade and experiment with wide impacts
Many changes in next few months.
DoE review coming up in June ‘99.
New director coming at Fermilab.
Changes at top
Spokes
Upgrade Management
H.Montgomery
H.Weerts
M.Tuts
H.Weerts (replace JC)
Not optimal………
Scrambled through May  August 1999

## Slide 14: Final Schedule for Run II
Sept-14-99
D0 collab mtg
New director (Witherell)
Slipped by 6 months
Realistic….
In the end accomplished this
~Sept 1999

## Slide 15: SMT
Memorable things & pictures
Eric Kajfasz (Marseille),
Expertise limited in D0, when started….
Delays at Micron Semiconductor dictated schedule
Fermilab “took” over Micron
Large effort at SiDet facility
D0 developed & trained a new set of Si experts  now working on new projects
Install
north

## Slide 16: Fiber tracker
Memorable things & pictures
VLPC
Fiber ribbon mounting
Critical:
Cylinders
Make ribbons of fibers
Install fibers
Measure fibers
CFT installation in solenoid
VLPC cryostats
Fibers landing
Signals out
Fiber routing nightmare

## Slide 17: Muon system
Memorable things & pictures
“ A Russian Affair”
Just HUGE
Best muon system (trigger) ever built
Replaced complete forward system
Trigger scintillators
Min Drift tubes
New trigger
Muon truss at Lab E
Muon C layer

## Slide 18: Triggers
Memorable things
L2
One area of close collaboration with CDF ( and MSU and U of Mich.)
Develop Alpha processors (Windows NT based)
One problem after the other ( more like disasters)
Prototype worked, but no production…… many man years gone
Started run…… replaced afterwards
Struggle for all involved
L3
Initially based on custom system for D0
Based on special expertise and Windows NT and custom hardware from Run I (VRBs)
Delays kept on occurring. Jan 2001:it would not work Implemented new solution based on standard data transfer and Linux processors
Old and new groups worked together and realized a working systems within months.

## Slide 19: Installation schemes….
Called “Tutti- Frutti” Land……used to plan

## Slide 20: Dzero moved in January 2001

## Slide 21: Dzero in and its people
February 2001

## Slide 25
1981
Get PhD
2014
1995
1989
1985
HW in DØ
2011
2007
2003
1999
DØ
Data
Intertwining of DØ and HW life
Complete overlap of MSU & DØ
HW at MSU
Anec: Nearly did not get tenure at MSU because of DØ

## Slide 26: Summary
Preparing this talk
Was good to go through history ( relive some)
DØ was large part of my life
Reminded me that I am getting old….
( technology has moved/is moving on)
It has been a privilege and great scientific & social experience to work on DØ and with colleagues from all over the globe.
While doing it…………
Looking back…………..
it was a struggle and challenging
it was simply a blast
It was good to see something like the upgrade come together and be an integral part of it.
Great to see DØ grow (in people & in science) and be part of that as well

## Slide 27: Summary
Preparing this talk
Was good to go through history ( relive some)
DØ was large part of my life
Reminded me that I am getting old….
( technology has moved/is moving on)
It has been a privilege and great scientific & social experience to work on DØ and with colleagues from all over the globe.
While doing it…………
Looking back…………..
it was a struggle and challenging
it was simply a blast
It was good to see something like the upgrade come together and be an integral part of it.
Great to see DØ grow (in people & in science) and be part of that as well
Thanks to all of
my DØ colleagues

## Slide 28
The End

## Slide 29
Upgrade
Lehman review March 1997
D0 more international ‘84  ‘97
?

## Slide 30
One institution from France so far….
Upgrade
Lehman review March 1997

## Slide 31: History
In 1995 was on Fermilab PAC. Lots of discussion about future….
Listened and made my own extrapolation
Still very optimistic numbers for Tevatron lumi for Run II and III/TeV33 ( did not happen)

## Slide 32
DØ