## Slide 1
CERN QXF
Conductor Procurement and Cable R&D
Ballarino, B. Bordini and L. Oberli
CERN, TE-MSC-SCD
LARP Meeting, Napa, 9 April 2013

## Slide 2
Outline
Cable specification and procurement
Medium and long term strategy
Cable development
Status of R&D activity
Cable geometries and first test results
On-going and future activities
Conclusions
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 3
Strand specification
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 4
Strand procurement (1/3)
RRP 132/169
PIT 192
Strand for Cabling Optimization (2012-2013)
5 km of RRP Nb-Ti 132/169 - Delivered in December 2012
Measured characteristics:
RRR > 150
Ic(12 T) > 700 A
Jc(12 T) > 2800 A/mm2
5 km of PIT Nb-Ta 192 - Delivered in March 2013
To be measured at CERN
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 5
Strand procurement (2/3)
Strand for Long Prototype Program (2016)
6 coils, 5.4 km of cable (UL=900 m),  220 km of strand
Procurement ( 440 km) to be launched by end 2014 – for deliveries as from
mid 2015
Strand for Short Model Program (2014-2015)
12 coils, 2 km of cable,  100 km of strand
2013
35 km of RRP 132/169
35 km of PIT 192
Technical specification out for tendering. Orders to be placed in May 2013
Deliveries as from November 2013
2014
30 km – to be ordered by beginning 2014
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 6
2012
2013
2014
2015
2016
10 km
Short Model: 30 km
Long Prototype: 400 km
Series
Short Model: 70 km
Strand procurement (2/3)
Series production:  2500 km of Nb3Sn strand
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 7
 2.5 tons
Nb3Sn strand procurement at CERN
Fresca 2
11 T
Hi-Lumi Quadrupole
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 8
Cable specification
433 A
496 A
538 A
Iop  25 % margin on the load line @ 1.9 K
P. Ferracin
Iop = 17320 A
Bpeak = 12.2 T
A. Ballarino
Napa, LARP Meeting, 9 April 2013
Notes: Ic(4.2K, 12T)= 632 A, i.e. Ic(1.9 K, 12 T)= 830 A, margin on load line at 1.9 K = 90 !

## Slide 9
Cable R&D Status
Assembly of short prototypes cables with copper and RRP strands
(RRP 132/169)
Cables assembled do not contain -yet - stainless steel core
PIT strands delivered in March 2013 – cabling in April 2013
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 10
Cable R&D
Objectives:
Develop an optimized cable geometry made from 40 strands Nb3Sn wires of 0.85 mm diameter meeting the electrical characteristics specified by the magnet design;
Limit the Ic degradation to < 5 %; assure RRR of extracted strands > 100;
Make cables from RRP and PIT strands – with the objective of possibly converging to the same cable geometry;
Perform a series of validation tests on strands and cables (FRESCA test station)
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 11
Cable R&D
 | Width (mm) | Mid-th (mm) | LT (mm) | Ic degr (%) | Keyst. (deg) | Compact. (%)
FRESCA 2* | 20.9 | 1.82 | 120 | < 5 | - | 87.5
11 T** | 14.7 | 1.25 | 100 | <4 | 0.79 | 87.3
* 40 strands of 1 mm diameter, PIT and RRP strands
** 40 strands of 0.7 mm diameter, RRP strands
Experience at CERN on Nb3Sn cables
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 12
Cable R&D
Width : 17.8 mm
Width compaction Cw = - 3.5
Mid-thickness : 1.50 and 1.53 mm
Keystone angle : 0.65 degree
Pitch length : 113 mm (17.5o) and 125 mm (16o)
Cw larger than its value for the FRESCA2 cable (- 4.6) but smaller than its value for the cable for the dipole DS 11 T (- 2.6).
A. Ballarino
Napa, LARP Meeting, 9 April 2013
Notes: With these parameters, the minor edge strain of the cable ( t/2d - 1) is equal to - 0.16 or - 0.177 respectively for a the mid-thickness of 1.5 mm and 1.53 mm.

## Slide 13
Fabrication of 17.8 mm wide cables without core RRP - 132/169
Cable R&D
Sample | Mid-thickness | Pitch length | Keystone angle
1 | ~ 1.53 mm | 113 mm | ~ 0.55 – 0.58 degree
2 | ~ 1.53 mm | 125 mm | ~ 0.55 – 0.58 degree
3 | ~ 1.50 mm | 113 mm | ~ 0.55 - 0.58 degree
4 | ~ 1.50 mm | 125 mm | ~ 0.55 – 0.58 degree
4 cables - 3 m long
2 mid thicknesses (1.53 mm and 1.50 mm)
2 pitch lengths (113 mm and 125 mm)
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 14
Cable R&D
PL=113 mm, 1.50 mm 3.9 % (Ic max. 5.8%) | PL=113 mm, 1.53 mm 2.9 % (Ic max. 6.6%)
PL=125 mm, 1.50 mm 2.7 % (Ic max. 4.4%) | PL=125 mm, 1.53 mm 0.52 % (Ic max. 2.4 %)
Mid-thickness
Pitch
4.3 K
12 T
4.3 K
12 T
4.3 K
12 T
4.3 K
12 T
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 15
Cable R&D
Average Ic degradation = 1.8 %
4.3 K
12 T
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 16
Cable R&D
T=4.3 K
Extracted strands –three
Is > 1000 A
A lot of margin…
A. Ballarino
Napa, LARP Meeting, 9 April 2013
Ic (A)
B (T)

## Slide 17
Mid-thickness ~ 1.50 mm, PL = 113 mm

## Slide 18
Mid-thickness ~ 1.50 mm, PL = 125 mm

## Slide 19
On-going activities
Cabling of Ruftherford cables with SS core – PIT and RRP
w=17.3 mm, mid-th=1.50 and 1.53 mm, LT=109 mm
After feedback from magnet winding, change - reduction- of
keystone angle to increase compaction on the large edge
and reduce compaction on the narrow edge. Objective:
improve mechanical stability and reduce filaments deformation
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 20
Cable Tests in FRESCA 1/2
Short Term Plan: test of cables (132/169 RRP, 192 PIT) with and without core by using the regular FRESCA power supply (up to 32 kA)
Critical current measurements at 4.3 K ( cable critical current at 12 T lower ~ 29 kA; cable self-field 0.8 T per 10 kA, maximum applied field 10 T)
Measurement of the stability current at 4.3 K and 1.9 K
Quench current measurements when simultaneously ramping the sample current and the applied magnetic field; ramp-rate dependence study
Measurements of the cable thermal stability (strip heaters impregnated with the cable samples)
Measurements of the quench propagation velocity
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 21
Cable Tests In FRESCA 2/2
Medium Term Plan : test of cables with and without core by using the 100 kA transformer
Critical current measurements at 4.3 K and 1.9 K with different applied field orientations to identify weak spots in the cables
Measurement of the stability current at 4.3 K an d 1.9 K up to 100 kA
Quench current measurements when simultaneously ramping the sample current and the applied magnetic field; ramp-rate dependence study
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 22
Additional studies
Critical current measurements of rolled wires (PIT and RRP)
Critical and Stability Current measurements of extracted strands
Critical Current Measurements of strands under axial and transversal load (UniGe)
Inter-strand resistance of cables with and without core
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 23
Conclusions
Conductor for R&D activity has been procured.
Conductor procurement strategy has been made. According to the
present plan of installation of the Hi-Lumi magnets, conductor
procurement for the series production shall be launched by
beginning 2016
Cable development has started. First results with the selected cable
geometry indicate low Ic degradation and sufficiently high RRR but possibly need for improvement of mechanical stability. Plan for development of both PIT and RRP cable is established
A. Ballarino
Napa, LARP Meeting, 9 April 2013

## Slide 24
Thanks for your attention