## Slide 1: Warm Front End and PXIE Status
Alexander Shemyakin
DOE Independent Project Review of PIP-II
16 June 2015

## Slide 2: Outline
PIP-II warm front end
PXIE status
Plans

## Slide 3: PIP-II warm front end
PIP-II: 800 MeV SRF linac constructed of CW-capable accelerating structures and operated initially at 1% duty factor
The warm front end prepares H- beam optimized for Booster injection and provides capabilities for future CW operation
  Ion Source (IS) and Low Energy Beam Transport (LEBT)
  Radio Frequency Quadrupole (RFQ)
  Medium Energy Transport (MEBT)

## Slide 4: PIP-II warm front end parameters
Parameters
  Output energy 2.1 MeV
    Below neutron production and high enough to mitigate space charge effects up to 10mA
  Peak beam current up to 10 mA (from µs to CW)
    5 mA nominal; 4 mA in macropulse for Booster injection
  Bunch-by-bunch selection capability
    For bucket injection to Booster and for future CW multi-user operation
  Output rms emittances: e<0.23 µm, eL<0.31 µm
  Proper vacuum, tails, and bunch extinction management
While the combination of parameters is unique, most of elements exist in other machines
  Exception: bunch-by-bunch selection

## Slide 5: Front end design concept
Standard scheme: Ion sources, LEBT, RFQ, MEBT
  Long MEBT to accommodate the chopping scheme
Attention to factors that may determine reliability and uptime
  Two ion sources
  Low gas flow to RFQ with a long LEBT
  Proven-design RFQ with low particle loss
  System of scrapers in LEBT and MEBT
    Passive and active parts of Machine Protection System
  Suppression of gas flow to SRF with a differential pumping section downstream of the MEBT absorber
LEBT
RFQ
MEBT
17 m

## Slide 6: R&D topics
Many ion machines have had problems with front ends
  R&D can mitigate risks for PIP-II and speed up commissioning
The most important R&D issues
  LEBT with low emittance growth compatible with chopping
  Reliable CW RFQ
  Bunch-by-bunch selection in MEBT
  Compatibility of high-power deposition in MEBT absorber with SRF downstream
Will be addressed by PXIE

## Slide 7: PIP-II Injector Experiment (PXIE)
PXIE is part of the R&D program that addresses the risks associated with the front end of PIP-II
  Warm front end + 2 cryomodules + HEBT + beam dump
  Nominal regime is CW; pulsed mode for commissioning and modelling the Booster injection
  Goal PXIE parameters replicate those for the corresponding section of PIP-II
    2mA from µs to CW; arbitrary 162.5 MHz bunch structure
30 keV
RFQ
MEBT
HWR
SSR1
HEBT
LEBT
2.1 MeV
10 MeV
25 MeV

## Slide 8: Ion source and LEBT - concept
Commercial 15mA DC ion source
  D-Pace, Inc.
  Modulator at extraction electrode
3 Solenoids with dipole correctors
Bending dipole
  Accommodate 2 ISs for PIP-II
  Part of Personnel Protection System
  Clearing secondary particles
Diagnostics
  Beam current monitors
  Emittance scanner
  Isolated diaphragms
Chopper
  Pre-chopping, MPS, pulse mode
  60 Hz, 1µs to DC
Possibility of partially un-neutralized transport
Possibility of scraping the beam at various locations
  Tail particles management
Ion Source
Chopper
Solenoids
Scheme of PXIE IS and LEBT in final configuration

## Slide 9: Ion source and LEBT - status
IS and LEBT are assembled, fully commissioned, and ready for RFQ arrival
  Straight configuration; dipole will be installed in FY16
  Beam current up to 10 mA in pulse and DC modes
    24 and 72 hrs runs at 5 mA; current stabilization loops
  At 5 mA, Twiss parameters reconstructed to the RFQ entrance are on target
X, mm
X’, mrad
en, rms = 0.13 µm

## Slide 10: RFQ
Designed and constructed at LBNL
  4 vane, 4 module brazed copper body
  Similar RFQ has been commissioned at IMP (Lanzhou, China) with 10 mA CW
All body machining and brazing is done
  All other parts are either on hand or will be delivered in coming weeks
Expected delivery in July 2015
Two 75 kW 162.5 MHz solid-state amplifiers are installed and commissioned
Water cooling system and LLRF are being prepared

## Slide 11: MEBT - concept
RFQ
Bunching cavity
Kickers
HWR
Quadrupoles
Absorber
Scrapers
Differential pumping
Space for diagnostics
Space for diagnostics
Transverse focusing with 2 doublets and 7 triplets
  First short section for beam matching; 1.14 m period after
Longitudinal focusing with 3 bunching cavities
Chopping system: Two TW kickers in sync + absorber
Last ~2 m are particle-free, UHV
Scrapers: 4 sets by 4 jaws in each
  Independently moving, electrically isolated, radiation- cooled plates

## Slide 12: MEBT – status
Magnets
  Quadrupoles and dipole correctors will be supplied by BARC, India
    Prototypes will be used for RFQ beam commissioning
  All power supplies are on hand
Prototype bunching cavity is being tested
  Ordering of 3 production cavities will follow
  Five 3 kW 162.5 MHz amplifiers have been ordered
    One has arrived and is been used in testing the prototype bunching cavity
A 4-jaws scraper set was tested with LEBT beam
  Two more sets are in production
Diagnostics is under development
  BPMs, toroids, insertion devices

## Slide 13: MEBT chopping system – status
Kicker
    One half of a 50 Ohm kicker prototype has been tested
      Excellent RF properties; full-power tested in vacuum
    Complete kicker prototype is being assembled
      Will be installed at MEBT in FY16
    Proof-of-principle operation of a ¼– power driver has been demonstrated
    If LDRD to develop a fast driver succeeds, the results may be used for a cheaper, 200 Ohm kicker version
      A prototype kicker is being developed as well
Absorber
    A ¼ - size prototype has been tested with an electron beam
      Will be tested with H- beam in FY16
      Design of a full-size absorber will follow

## Slide 14: Beyond the warm front end
Cryomodules: Half-Wave Resonator (HWR) and Single- Spoke Resonator (SSR1) cryomodules
  HWR: 162.5 MHz, 2-10 MeV; SSR1: 325 MHz, 10-25 MeV
  Under construction; expected to be delivered in FY17
  Will be covered in V. Yakovlev’s presentation
  Indian contribution:
    some of SSR1cavities; 10 kW 325 MHz amplifiers;
    participation in LLRF and RF protection systems
High Energy Beam Transport (HEBT) and beam dump
  To analyze properties of the beam coming out of SRF
    Emittance, halo, stability, bunch extinction
  To safely accept 50 kW beam
  At the stage of conceptual design

## Slide 15: PXIE infrastructure
CMTF building, housing PXIE, has all required capacity
  Cryo, power, water
  Distribution systems are being designed and implemented
All components for the PXIE cave are on hand
Cryoplant

## Slide 16: PXIE commissioning plan
FY15
  install RFQ; prepare the RFQ beam characterization setup
FY16
  Commission RFQ (RF and beam)
  Install most of the MEBT magnets and kicker prototypes
FY17
  Finalize design of all MEBT components
  Receive both cryomodules
FY18
  Install final MEBT; demonstrate bunch-by-bunch selection
  RF commissioning of both cryomodules; pass a beam through
FY19: final beam parameters

## Slide 17: Warm front end commissioning
After RFQ RF commissioning, characterize beam (FY16)
  Using 1st MEBT section, essential diagnostics, and a temporary beam dump; 10 µs pulse first
Increase the pulse length to 10 kW CW (FY16)
Install 4 more triplets (FY16)
  With prototypes of kickers and absorber
  Test the absorber prototype with H- beam (FY16)
  Pass the beam through the kickers
    Test EM characteristics by applying 162.5 or 81.25 MHz CW RF and observing the bunch shift with BPMs (FY17)
    Test kicker protection system and their survivability (FY17)
Install full- length MEBT with final elements (FY18)
  demonstrate bunch-by-bunch selection (FY18)
  Test vacuum compatibility of MEBT with SRF (FY19)

## Slide 18: Summary
At the end of the PXIE R&D program, the critical technologies of the PIP-II Linac front end will be validated, accomplishing
  Acceleration of a 2 mA CW beam in low-beta SRF
  Demonstration of bunch by bunch selection using state of the art chopping system
  Specification of conditions for reliable operation of SRF cavities in vicinity of a high power MEBT absorber
  LFD compensation in pulsed operation of SSR1
  Detailed characterization of beam parameters, dynamics, and stability